## Wx
PROJECT REPORT
Group | SWP490_G23
Week | 07/10/2020-13/10/2020
I. Status Report
# | Project Work Item | Ask the teacher | Notes (Work Item in Details)
1 | Finish report 2 | Completed | Finish report 2 with part quality of project. Research from PM and test leader who working at Fsoft
2 | Finish report 3 | In Progress | Not finished drawing mockup of project
3 | Implememt report 4 | In Progress | Draw architecture of system, package diagram, class diagram, sequence diagram.
4 | Research about HL7 | In Progress | Research about hl7 and software hospital record keeping convention.
5 | Coding CMA | In Progress | Implement CMA with spring boot
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Finish report 2 | All | Finish report 2 with part quality of project. Research from PM and test leader who working at Fsoft
2 | Finish report 3 | All | Not finished drawing mockup of project
3 | Implememt report 4 | All | Draw architecture of system, package diagram, class diagram, sequence diagram.
4 | Research about HL7 | All | Research about hl7 and software hospital record keeping convention.
5 | Coding CMA | DucDT | Implement CMA with spring boot
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Finish report 3 | In Progress | Not finished drawing mockup of project
2 | Implememt report 4 | In Progress | Not define detail class diagram
3 | Research about HL7 | In Progress | Research about hl7 and software hospital record keeping convention.
4 | Coding CMA | In Progress | Implement CMA with spring boot
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Finish report 4 | 17/10/2020
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes