## Wx
PROJECT REPORT
Group | SWP490_G23
Week | 14/10/2020-20/10/2020
I. Status Report
# | Project Work Item | Ask the teacher | Notes (Work Item in Details)
1 | Finish report 4 | In Progress | Hoàn chỉnh những diagram trong report 4.
2 | Draw mockup of project | In Progress | Vẽ mockup cho từng chức năng của hệ thống.
3 | Edit ERD | Completed | Chỉnh sửa ERD theo chuẩn mới.
4 |  | In Progress
5 |  | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Finish report 4 | All | Trang NT vẽ class diagram và ThienND vẽ sequence diagram.
2 | Draw mockup of project | All | Họp nhóm tất cả cùng cho ý kiến để vẽ ra màn hình.
3 | Edit ERD | All | Chỉnh sửa lại ERD theo chuẩn mới và xác định attribute.
4 |  | All
5 |  | All
III. Project Issues
# | Project Issue | 25/10/2020 | Notes (Solution, Suggestion, etc.)
1 | Finish report 4 | In Progress | Chưa hoàn chỉnh được class diagram.
2 | Draw mockup of project | In Progress | Còn một số chức năng chưa vẽ xong mockup.
3 |  | In Progress
4 |  | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Finish report 4 | 23/10/2020
| Draw mockup of project | 25/10/2020
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes