## Wx
PROJECT REPORT
Group | SWP490_G23
Week | 21/10/2020-27/10/2020
I. Status Report
# | Project Work Item | Ask the teacher | Notes (Work Item in Details)
1 | Finish report 4 | In Progress
2 | Draw mockup of project | In Progress
3 | Traning code | Completed
4 | Code back and font end | In Progress
5 | Research test for report 5 | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Finish report 4 | All
2 | Draw mockup of project | All
3 | Traning code | All
4 | Code back and font end | TrangNT&DucDT & ThienND
5 | Research test for report 5 | TrangLTT
III. Project Issues
# | Project Issue | 25/10/2020 | Notes (Solution, Suggestion, etc.)
1 | Finish report 4 | In Progress | Nhóm chưa có description cho database và class diagram
2 | Draw mockup of project | In Progress | Nhóm đã vẽ xong hết chức năng, tuy nhiên chưa vẽ lại bằng tool
3 |  | In Progress
4 |  | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Finish report 4 | 30/10/2020
| Draw mockup of project | 30/10/2020
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes