## Trang tính1
Responsibility Assignment Matrix
| Task Name | Predecessor | Thien | Duc | Trang | Thu trang | Khanh | W - works on
Project management | 1.1 Project Charter | None | W | W | W, Q | W | W | Q - Quality Reviewer
| 1.2 Project Plan | None | W | W | W, Q | W | W
| 1.3 Support plan | None | W | W | W, Q | W | W
Requirement | 2.1 System Requirement | None | W | W | W, Q | W, Q | W, Q
| 2.2 Business rules | None | W | W | W, Q | W, Q | W, Q
| 2.3 Information | None | W | W | W, Q | W, Q | W, Q
Design | 3.1 Architecture design | 2.1 System Requirement | W | W | W | W | W, Q
| 3.2 Details design | 3.1 Architecture design | W | W | W | W | W, Q
| 3.3 Detect software and hardware needed | 3.1 Architecture design | W | W | W | W | W, Q
| 3.4 UI, UX Client | 2.1 System Requirement | W, Q | Q | Q | Q | Q
Development | 4.1 Develop database and backend web services | 3.1 Architecture design | W | W, Q | W | W | W
| 4.2 Develop Frontend | 2.1 System Requirement | W, Q | W | W | W | W
| 4.3 Connect Frontend with API | 4.1 Develop database and backend web services | W, Q | W | W | W | W
Testing | 5.1 Interface testing | 4.2 Develop Frontend | W | W | W | W, Q | W
| 5.2 Functional testing | 4.1 Develop database and backend web services | W | W | W | W, Q | W
| 5.3 Security testing | 4.1 Develop database and backend web services | W | W | W | W, Q | W
Deployment | 6.1 Deploy anlpha version | Testing | W, Q | W, Q
| 6.2 Deploy free-trial version |  | W, Q | W, Q
| 6.3 Deploy final version |  | W, Q | W, Q