## Trang tính1
Project Risks
Name | Description | severity | Probabilty of Occurrence | Action
Member leave the project | They dont wanna continue | High | Low | 1. Choose member have good sense and friendly. 2. Make them feel excited about the project.
Bad performance | Some feature dont have good performance because source code is not optimized | High | Medium | 1. Optimized each fuction 2. Optimized finnal source code
Member lack knowledge | Members do not have a good knowledge of many technical aspects | Medium | High | 1. Training for each other 2. Learning on internet and coursera
Change Requirement | some feature be block by facebook, shoppe, tiki,.. | Medium | Low | 1. Disable feature and find new way for that feature
Security | lost user data becouse, the system be hacked by hacker | High | Low | 1. "Using token for improving backend security" 2. Add more agorithm for hash private infomation
Bad UX | Some feature have bad ui ux with new user | Medium | Low | 1. Update UI UX follow feedback 2. Use guidline for new user