## Trang tính1
Project Schedule
| Task Name | Predecessor | Start | End | Duration(day) | Resources
Project management | 1.1 Project Charter | None | 2020-09-01 | 2020-09-15 | 14
| 1.2 Project Plan | None | 2020-09-15 | 2020-09-17 | 2
| 1.3 Support plan | None | 2020-09-17 | 2020-09-20 | 3
Requirement | 2.1 System Requirement | None | 2020-09-01 | 2020-09-20 | 19
| 2.2 Business rules | None | 2020-09-01 | 2020-09-10 | 9
| 2.3 Information | None | 2020-09-01 | 2020-09-10 | 9
Design | 3.1 Architecture design | 2.1 System Requirement | 2020-09-10 | 2020-10-30 | 50
| 3.2 Details design | 3.1 Architecture design | 2020-09-10 | 2020-10-30 | 50
| 3.3 Detect software and hardware needed | 3.1 Architecture design | 2020-09-10 | 2020-10-20 | 40
| 3.4 UI, UX Client | 2.1 System Requirement | 2020-09-10 | 2020-10-30 | 50
Development | 4.1 Develop database and backend web services | 3.1 Architecture design | 2020-10-15 | 2020-12-20 | 66
| 4.2 Develop Frontend | 2.1 System Requirement | 2020-10-15 | 2020-12-20 | 66
| 4.3 Connect Frontend with API | 4.1 Develop database and backend web services | 2020-10-15 | 2020-12-20 | 66
5 | Testing |  |  |  | 0
Testing | 5.1 Interface testing | 4.2 Develop Frontend | 2020-10-15 | 2020-12-25 | 71
| 5.2 Functional testing | 4.1 Develop database and backend web services | 2020-10-15 | 2020-12-25 | 71
| 5.3 Security testing | 4.1 Develop database and backend web services | 2020-10-15 | 2020-12-25 | 71
Deployment | 6.1 Deploy anlpha version | Testing | 2020-10-30 | 2020-10-30 | 0
| 6.2 Deploy free-trial version |  | 2020-11-20 | 2020-11-20 | 0
| 6.3 Deploy final version |  | 2020-12-20 | 2020-12-25 | 5