## Wx
PROJECT REPORT
Group | SWP490_G23
Week | 16/09/2020-22/09/2020
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Define (As Is and Pain Point of exist system) | Completed | Business description of the clinic
2 | Survey system exists | Completed | System's name BigSoft, Used by Eye clinic management system.
3 | Create a table write of each member's ability | Completed | Ask everyone about the ability and the number of hours a day is spent on the project
4 | Thinking about changing the project name | Pending | Think the project name is close to the idea
5 | Analyze and show basic system features of system exist according each Actor | Completed | Analysis via the role of system has been screen shot of system
6 | Complete report 1 | In Progress | Introduce project
7 | Study UML | Completed | Each person explores a section and others Q&A about it.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Define (As Is and Pain Point of exist system) | All | Ask Bigsoft developer and clinic doctor
2 | Survey system exists | DucDN | Know the clinic and the developer project Bigsoft
3 | Create a table write of each member's ability | TrangNT | Take note about ability
4 | Thinking about changing the project name | All | Think the project name is close to the idea
5 | Analyze and show basic system features of system exist according each Actor | All | Functional analysis via the role of system has been DucDT screen shot and DucDT used
6 | Complete report 1 | TrangNT | Document for Introduce project
7 | Study UML | All | Each person explores a section and others Q&A about it.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Thinking about changing the project name | Pending | Consult the teacher. the team cannot come up with a name for the project that matches the right idea
| Complete report 1 | In Progress | Define Major Features and Project Scope &amp; Limitations.
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Thinking about changing the project name | 24/09/2020 | Ask the teacher and think more
| Complete report 1 | 25/09/2020 | All groups must be unified about new system
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes