## Wx
PROJECT REPORT
Group | SWP490_G23
Week | 23/09/2020-29/09/2020
I. Status Report
# | Project Work Item | Ask the teacher | Notes (Work Item in Details)
1 | Thinking about changing the project name | Completed | Ask the teacher
2 | Survey system exists of ABClinic | Completed | Go to ABClinic meet with doctor Kien
3 | Finish report 1 | Completed | Finish report 1 follow template
4 | Report 2 | In Progress | Work follow template report 2
5 | Add AS - IS, PAINT POIT for report 1 | Completed | Detail major features
6 | The system's TO-BE evaluation by a specialist | Completed | Business must be detailed
7 | Training knowledge for members | Completed | Training github, Spring Framework
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Thinking about changing the project name | All | Ask the teacher about name
2 | Survey system exists of ABClinic | All | Go to ABClinic at 12:00 AM Thursday
3 | Finish report 1 | All | Finish report 1 follow template
4 | Report 2 | All | Work follow template report 2
5 | add AS - IS, PAINT POIT for reporting 1 | All | Detailed function analysis and listing
6 | The system's TO-BE evaluation by a specialist | DucDT | Review business detail by doctor and manager IT
7 | Training knowledge for members | All | DucDT traning to team members
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Complete report 2 | In Progress | Some articles do not know how to write content and don't know time.
Pending
Pending
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Complete report 2 | 2020-02-10 | Unfinished a large number of plans detail
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes