## Trang tính1
Work Breakdown Structure
1 | Project management | Initation phase to define what to do | Start | End
| 1.1 Project Charter | Define objectives, scope, high-level implementation plan and deliverables of the project | 2020-09-01 | 2020-09-15
| 1.2 Project Plan | Define the goal, evaluate options, plan carefully, and think about what might happen | 2020-09-15 | 2020-09-17
| 1.3 Support plan | Define plan supporting, rules in supporting, the list of things to transfer in advance of this job | 2020-09-17 | 2020-09-20
2 | Requirement | Collect requirements from stakeholders and define it
| 2.1 System Requirement | Collect and define requirements about the system | 2020-09-01 | 2020-09-20
| 2.2 Business rules | Collect and define validate business rules of project | 2020-09-01 | 2020-09-10
| 2.3 Information | Get information about data models | 2020-09-01 | 2020-09-10
3 | Design | Design how to do and how this product looks like and how user experience and our structure
| 3.1 Architecture design | Design software components and their interfaces | 2020-09-10 | 2020-10-30
| 3.2 Details design | Details of each component, the element from Architecture design | 2020-09-10 | 2020-10-30
| 3.3 Acquire needed software and hardware | Define software, hardware the project needs and acquire to client | 2020-09-10 | 2020-10-20
| 3.4 UI, UX Client | Design UI follow requirment and graphic design trend | 2020-09-10 | 2020-10-30
4 | Development | Developing project
| 4.1 Develop database and backend web services | Create a database based on the design, backend development based on the requirements, the structure and on the designed database | 2020-10-15 | 2020-12-20
| 4.2 Develop Frontend | Develop frontend based on requirements, structure and work with backend to unify api | 2020-10-15 | 2020-12-20
| 4.3 Connect Frontend with API | Connect frontend and backend with api | 2020-10-15 | 2020-12-20
5 | Testing | Testing product
| 5.1 Interface testing | Testing user interface | 2020-10-15 | 2020-12-25
| 5.2 Functional testing | Testing business logic to check whether features meet story acceptance criteria or not | 2020-10-15 | 2020-12-25
| 5.3 Security testing | Testing data and authentication and some cases require higher security | 2020-10-15 | 2020-12-25
6 | Deployment | Deploying product
| 6.1 Deploy anlpha version | deploy server for tester | 2020-10-30 | 2020-10-30
| 6.2 Deploy free-trial version | deploy server for 10-20 user | 2020-11-20 | 2020-11-20
| 6.3 Deploy final version | deploy server for greater than 1000 user | 2020-12-20 | 2020-12-25