

**CAPSTONE PROJECT REPORT**

**HVT**

**DIGITAL TRANSFORMATION**

**SWP490\_G24**

Vu Bao Yen SE05610

Pham Trong Kim SE05423

**Project team**

Nguyen Tung Lam SE05790

Nguyen Thi Kim Loan SE05636

**Supervisor** Mr. Tran Binh Duong

**Project code** HVT Digital Transformation

HVT Digital Transformation – Final Report v.1.1.9

**TABLE OF CONTENTS**

**CHAPTER 1: INTRODUCTION ................................................................................................. 16 1. PROJECT INFORMATION............................................................................................. 16 2. PROJECT TEAM.............................................................................................................. 16**

**2.1. Supervisor................................................................................................................... 16 2.2. Team members........................................................................................................... 16 3. INITIAL IDEA .................................................................................................................. 17 3.1. Background ................................................................................................................ 17 3.2. Digital transformation phase ..................................................................................... 17 3.3. Problem ...................................................................................................................... 18 3.4. Existing Products ....................................................................................................... 18 3.5. Solution....................................................................................................................... 23 3.6. System Proposals........................................................................................................ 24 CHAPTER 2: PROJECT MANAGEMENT PLAN..................................................................... 27 1. INTRODUCTION ............................................................................................................. 27 1.1. Document Description................................................................................................ 27 1.2. Document Scope ......................................................................................................... 27 2. PROJECT OVERVIEW.................................................................................................... 27 2.1. Project description ..................................................................................................... 27 2.2. Project Scope .............................................................................................................. 27 2.3. Standard Objectives................................................................................................... 28 3. PROJECT TEAM.............................................................................................................. 28 3.1. Software Process Model ............................................................................................. 28 3.2. Project Lifecycle ......................................................................................................... 29 3.3. Roles and Responsibilities.......................................................................................... 30 4. TOOLS AND INFRASTRUCTURES............................................................................... 31 4.1. Hardware.................................................................................................................... 31 4.2. Software...................................................................................................................... 31 5. SCHEDULES..................................................................................................................... 32 5.1. Detail Schedules.......................................................................................................... 32 5.2. Milestones and Deliverable ........................................................................................ 37 6. COMMUNICATION MANAGEMENT........................................................................... 38 6.1. Stakeholders and Contacts......................................................................................... 38 6.2. Communication Management Approach .................................................................. 38 6.3. Communication Requirements .................................................................................. 38 6.4. Communication Method and Technologies ............................................................... 38 7. RISK MANAGEMENT..................................................................................................... 39**

2/579

HVT Digital Transformation – Final Report v.1.1.9

**7.1. Risk Management Approach ..................................................................................... 39 7.2. Risk Identification...................................................................................................... 39 7.3. Risk Qualification and Prioritization......................................................................... 40 7.4. Risk Monitoring ......................................................................................................... 40 7.5. Risk Register............................................................................................................... 41 7.6. Risk Implement .......................................................................................................... 52**

**8. QUALITY MANAGEMENT ............................................................................................ 55 8.1. Quality Management Overview ................................................................................. 55 8.2. Quality Planning......................................................................................................... 55 8.3. Quality Control .......................................................................................................... 57**

**CHAPTER 3: SOFTWARE REQUIREMENTS SPECIFICATION .......................................... 58 1. INTRODUCTION ............................................................................................................. 58 1.1. Purpose ....................................................................................................................... 58 1.2. Scope........................................................................................................................... 58 1.3. Overview..................................................................................................................... 58 2. OVERALL DESCRIPTION.............................................................................................. 58 2.1. Scope of work ............................................................................................................. 58 3. BUSINESS PROCESS MANAGEMENT ......................................................................... 59 3.1. Business Process of Manage Emulation..................................................................... 59 3.2. Business rules ............................................................................................................. 59 3.3. Modeling the problem "Assignment of Red Stars"................................................... 61 4. FUNCTIONAL REQUIREMENTS.................................................................................. 63 4.1. Module 1: Manage Account ....................................................................................... 63 4.2. Module 2: Manage Teacher ....................................................................................... 91 4.3. Module 3: Manage Class.......................................................................................... 102 4.4. Module 4: Manage Timetable .................................................................................. 122 4.5. Module 5: Manage Violation.................................................................................... 132 4.6. Module 6: Manage School Year ............................................................................... 152 4.7. Module 7: Manage Violation Entering Time........................................................... 162 4.8. Module 8: Assign Red Star....................................................................................... 170 4.9. Module 9: Manage Emulation.................................................................................. 181 4.10. Module 10: Manage School Rank ............................................................................ 206 4.11. Module 11: Manage Newsletter ............................................................................... 254 5. NON-FUNCTIONAL REQUIREMENTS ...................................................................... 271 5.1. Availability ............................................................................................................... 271 5.2. Usability.................................................................................................................... 271 5.3. Security..................................................................................................................... 272**

3/579

HVT Digital Transformation – Final Report v.1.1.9

**5.4. Performance ............................................................................................................. 272 CHAPTER 4: SOFTWARE DETAIL DESIGN......................................................................... 273 1. ARCHITECTURE DESIGN ........................................................................................... 273 1.1. Introduction.............................................................................................................. 273 1.2. Deployment View...................................................................................................... 273 1.3. Logical View ............................................................................................................. 274 1.4. User Case View......................................................................................................... 276 1.5. Implementation View ............................................................................................... 278 1.6. Detail Design............................................................................................................. 278 2. DATABASE DESIGN...................................................................................................... 448 2.1. Table Database ......................................................................................................... 448 2.2. Database Dictionary ................................................................................................. 448 3. INTERFACE DESIGN.................................................................................................... 455 3.1. Module 1: Manage Account ..................................................................................... 455 3.2. Module 2: Manage Teacher ..................................................................................... 467 3.3. Module 3: Manage Class.......................................................................................... 472 3.4. Module 4: Manage Timetable .................................................................................. 476 3.5. Module 5: Manage Violation.................................................................................... 479 3.6. Module 6: Manage School Year ............................................................................... 480 3.7. Module 7: Manage Violation Entering Time........................................................... 480 3.8. Module 8: Assign Red Star....................................................................................... 481 3.9. Module 9: Manage Emulation.................................................................................. 481 3.10. Module 10: Manage School Rank ............................................................................ 482 3.11. Module 11: Manage Newsletter ............................................................................... 482 CHAPTER 5: SOFTWARE TEST DOCUMENTATION......................................................... 483 1. INTRODUCTION ........................................................................................................... 483 1.1. Purpose ..................................................................................................................... 483 1.2. Overview................................................................................................................... 483 2. TEST PLAN..................................................................................................................... 483 2.1. Introduction.............................................................................................................. 483 2.2. Requirements for Test.............................................................................................. 486 2.3. Test Strategy............................................................................................................. 486 2.4. Resource ................................................................................................................... 488 2.5. Test Milestones......................................................................................................... 488 3. TEST REPORT ............................................................................................................... 489 3.1. Unit Test ................................................................................................................... 489 3.2. Integration Test........................................................................................................ 491**

4/579

HVT Digital Transformation – Final Report v.1.1.9

**3.3. System Test............................................................................................................... 492 3.4. Bug Log..................................................................................................................... 493**

**3.5. Evaluating the solution of problem “Assignment of Red Stars” with Genetic Algorithm............................................................................................................................. 494**

**CHAPTER 6: SOFTWARE USER’S MANUAL ....................................................................... 495 1. PURPOSE ........................................................................................................................ 495 2. USER’S GUIDE............................................................................................................... 495**

**2.1. Module 1: Manage Account ..................................................................................... 495 2.2. Module 2: Manage Teacher ..................................................................................... 509 2.3. Module 3: Manage Class.......................................................................................... 515 2.4. Module 4: Manage Timetable .................................................................................. 526 2.5. Module 5: Manage Violation.................................................................................... 531 2.6. Module 6: Manage School Year ............................................................................... 539 2.7. Module 7: Manage Violation Entering Time ........................................................... 543 2.8. Module 8: Assign Red Star....................................................................................... 546 2.9. Module 9: Manage Emulation.................................................................................. 552 2.10. Module 10: Manage School Rank ............................................................................ 563 2.11. Module 11: Manage Newsletter ............................................................................... 570**

5/579

HVT Digital Transformation – Final Report v.1.1.9

**TABLE OF FIGURES**

*Figure 1: Screenshot of website 1.............................................................................................................................................................. 19 Figure 2: Screenshot of website 2.............................................................................................................................................................. 19 Figure 3: Screenshot of website 3.............................................................................................................................................................. 19 Figure 4: Screenshot of website 4.............................................................................................................................................................. 19 Figure 5: Enter the subject list in Timetable creation software................................................................................................... 20 Figure 6: Enter the class list in Timetable creation software....................................................................................................... 20 Figure 7: Enter the teacher list in Timetable creation software.................................................................................................. 21 Figure 8: Enter the grade list in Timetable creation software ..................................................................................................... 21 Figure 9: Timetable of all class as an Excel file................................................................................................................................. 22 Figure 10: Timetable of all teachers as an Excel file....................................................................................................................... 22 Figure 11: Morning timetable of all class as HTML folder........................................................................................................... 23 Figure 12: Timetable of teacher as HTML folder.............................................................................................................................. 23 Figure 13: Scrum model................................................................................................................................................................................. 28 Figure 14: Project Organization Structure ........................................................................................................................................... 30 Figure 15: Schedule for Initiating Phase ............................................................................................................................................... 32 Figure 16: Schedule for Sprint 1................................................................................................................................................................ 33 Figure 17: Schedule for Sprint 2................................................................................................................................................................ 34 Figure 18: Schedule for Sprint 3................................................................................................................................................................ 35 Figure 19: Schedule for Sprint 4................................................................................................................................................................ 36 Figure 20: Business process flow of "Manage Emulation"............................................................................................................ 59 Figure 21: Use Case Diagram of Manage Account Module ......................................................................................................... 63 Figure 22: Activity diagram for login...................................................................................................................................................... 66 Figure 23: Activity diagram for logout.................................................................................................................................................... 68 Figure 24: Activity diagram for view the personal information .................................................................................................. 70 Figure 25: Activity diagram for edit the personal information.................................................................................................... 73 Figure 26: Activity diagram for change password............................................................................................................................. 77 Figure 27: Activity diagram for reset multiple account password ............................................................................................. 80 Figure 28: Activity diagram for view account list.............................................................................................................................. 82 Figure 29: Activity diagram for search account................................................................................................................................. 83 Figure 30: Activity diagram for Create an account.......................................................................................................................... 87 Figure 31: Activity diagram for delete account................................................................................................................................... 90 Figure 32: Use Case Diagram of Manage Teacher Module ......................................................................................................... 91 Figure 33: Activity diagram for view teacher list............................................................................................................................... 92 Figure 34: Activity diagram for search teacher.................................................................................................................................. 93 Figure 35: Activity diagram for add teacher........................................................................................................................................ 96 Figure 36: Activity diagram for edit teacher........................................................................................................................................ 99 Figure 37: Activity diagram for delete teacher.................................................................................................................................102 Figure 38: Use Case Diagram of Manage Class Module.............................................................................................................102 Figure 39: Activity diagram for view class list..................................................................................................................................104 Figure 40: Activity diagram for search class.....................................................................................................................................105 Figure 41: Activity diagram for edit information of the class....................................................................................................108 Figure 42: Activity Diagram of Change status of class.................................................................................................................111 Figure 43: Activity Diagram of Delete gifted class.........................................................................................................................121 Figure 44: Use Case Diagram of Manage Timetable Module ...................................................................................................122 Figure 45: Activity Diagram of View the timetable of a class....................................................................................................124 Figure 46: Activity diagram for search class timetable.................................................................................................................125 Figure 47: Activity diagram for view the timetable of teacher...................................................................................................127 Figure 48: Activity diagram for search teacher timetable ...........................................................................................................128 Figure 49: Activity Diagram for update new timetable.................................................................................................................131 Figure 50: Use Case Diagram of Manage Violation......................................................................................................................132*

6/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 51: Activity Diagram for view violation type list...............................................................................................................134 Figure 52: Activity Diagram for view violation list.........................................................................................................................135 Figure 53: Activity Diagram for edit violation type........................................................................................................................138 Figure 54: Activity Diagram for add violation type........................................................................................................................141 Figure 55: Activity Diagram for delete violatoin type ...................................................................................................................143 Figure 56: Activity Diagram for edit violation..................................................................................................................................146 Figure 57: Activity Diagram of Add violation ...................................................................................................................................149 Figure 58: Activity Diagram for delete violatoin .............................................................................................................................152 Figure 59: Use Case Diagram of Manage School Year................................................................................................................152 Figure 60: Activity Diagram for View school year list..................................................................................................................154 Figure 61: Activity Diagram for Add new school year..................................................................................................................156 Figure 62: Activity Diagram for Add new school year..................................................................................................................159 Figure 63: Activity Diagram for Delete school year.......................................................................................................................161 Figure 64: Use Case Diagram of Manage Violation Entering Time.......................................................................................162 Figure 65: Activity Diagram for View violation entering time...................................................................................................163 Figure 66: Activity Diagram for Add violation entering time.....................................................................................................166 Figure 67: Activity Diagram for Delete violation entering time ...............................................................................................169 Figure 68: Use Case Diagram of Assign Red Star..........................................................................................................................170 Figure 69: Activity Diagram for View assign Red Star.................................................................................................................172 Figure 70: Activity Diagram for Search assign Red Star.............................................................................................................173 Figure 71: Activity Diagram for Download assign Red Star......................................................................................................175 Figure 72: Activity Diagram for Create assign Red Star.............................................................................................................178 Figure 73: Activity Diagram for Delete assign Red Star..............................................................................................................180 Figure 74: Use Case Diagram of Manage Emulation....................................................................................................................181 Figure 75: Activity Diagram for View violation of a class..........................................................................................................183 Figure 76: Activity Diagram for Search violation of a class......................................................................................................185 Figure 77: Activity Diagram for Add violation of a class............................................................................................................189 Figure 78: Activity Diagram for Edit violation of a class............................................................................................................192 Figure 79: Activity Diagram for View change request ..................................................................................................................194 Figure 80: Activity Diagram for Search change request..............................................................................................................195 Figure 81: Activity Diagram for Accept change request...............................................................................................................197 Figure 82: Activity Diagram for Reject change request................................................................................................................199 Figure 83: Activity Diagram for Cancel edit request.....................................................................................................................202 Figure 84: Activity Diagram for View violation history................................................................................................................204 Figure 85: Activity Diagram for Search violation history............................................................................................................205 Figure 86: Use Case Diagram of Manage School Rank ...............................................................................................................206 Figure 87: Activity Diagram for View week rank.............................................................................................................................208 Figure 88: Activity Diagram for Search week rank.........................................................................................................................210 Figure 89: Activity Diagram for Download week rank .................................................................................................................211 Figure 90: Activity Diagram for View month rank..........................................................................................................................213 Figure 91: Activity Diagram for Search month rank......................................................................................................................215 Figure 92: Activity Diagram for Download month rank...............................................................................................................216 Figure 93: Activity Diagram for View semester rank.....................................................................................................................218 Figure 94: Activity Diagram for Search semester rank.................................................................................................................219 Figure 95: Activity Diagram for Download semester rank..........................................................................................................221 Figure 96: Activity Diagram for View year rank..............................................................................................................................223 Figure 97: Activity Diagram for Search year rank..........................................................................................................................224 Figure 98: Activity Diagram for Download year rank...................................................................................................................225 Figure 99: Activity Diagram for View school rank week history..............................................................................................227 Figure 100: Activity Diagram for View school rank month history.........................................................................................228 Figure 101: Activity Diagram for View school rank semester history....................................................................................230 Figure 102: Activity Diagram for View school rank year history.............................................................................................231 Figure 103: Activity Diagram for Create rank week ......................................................................................................................234*

7/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 104: Activity Diagram for Edit rank week............................................................................................................................236 Figure 105: Activity Diagram for Update week rank .....................................................................................................................239 Figure 106: Activity Diagram for Create rank month....................................................................................................................241 Figure 107: Activity Diagram for Edit rank month.........................................................................................................................243 Figure 108: Activity Diagram for Create rank semester...............................................................................................................246 Figure 109: Activity Diagram for Edit rank semester....................................................................................................................249 Figure 110: Activity Diagram for Create rank year.......................................................................................................................251 Figure 111: Activity Diagram for Edit rank year.............................................................................................................................253 Figure 112: Use case Diagram of Manage Newsletter..................................................................................................................254 Figure 113: Activity Diagram for View home page.........................................................................................................................256 Figure 114: Activity Diagram for Search newsletter......................................................................................................................258 Figure 115: Activity Diagram for View detail newsletter.............................................................................................................260 Figure 116: Activity Diagram for Add a newsletter........................................................................................................................263 Figure 117: Activity Diagram for Edit newsletter............................................................................................................................266 Figure 118: Activity Diagram for View newsletter request .........................................................................................................268 Figure 119: Activity Diagram for Search newsletter request.....................................................................................................269 Figure 120: Activity Diagram for Change status of newsletter request.................................................................................271 Figure 121: Deployment View...................................................................................................................................................................273 Figure 122: Project Architecture.............................................................................................................................................................274 Figure 123: Spring Boot Achitecture .....................................................................................................................................................274 Figure 124: Use Case Diagram - All Use............................................................................................................................................276 Figure 125: Use Case Diagram – Users have account..................................................................................................................277 Figure 126: Package Diagram..................................................................................................................................................................278 Figure 127: Class Diagram of Module 1 – Manage Account.....................................................................................................278 Figure 128: Class Diagram of Module 2 – Manage Teacher.....................................................................................................279 Figure 129: Class Diagram of Module 3 – Manage Class..........................................................................................................279 Figure 130: Class Diagram of Module 4 – Manage Timetable.................................................................................................279 Figure 131: Class Diagram of Module 5- Manage Violation.....................................................................................................280 Figure 132: Class Diagram of Module 6 – Manage School Year.............................................................................................280 Figure 133: Class Diagram of Module 7 – Manage Violation Entering Time ...................................................................280 Figure 134: Class Diagram of Module 8 – Assign Red Star.......................................................................................................281 Figure 135: Class Diagram of Module 9 – Manage Emulation ................................................................................................281 Figure 136: Class Diagram of Module 10 – Manage School Rank.........................................................................................282 Figure 137: Class Diagram of Module 11 – Manage Newsletter.............................................................................................282 Figure 138: Class Diagram of Controller...........................................................................................................................................283 Figure 139: Class Diagram of Service..................................................................................................................................................322 Figure 140: Class Diagram of Entity.....................................................................................................................................................389 Figure 141: Class Diagram of Exception.............................................................................................................................................397 Figure 142: Class Diagram of Security ................................................................................................................................................398 Figure 143: Class Diagram of Repository...........................................................................................................................................403 Figure 144: Class Diagram of ResponseDto......................................................................................................................................407 Figure 145: Class Diagram of RequestDto.........................................................................................................................................408 Figure 146: Class Diagram of Constant...............................................................................................................................................408 Figure 147: Sequence Diagram of UC-1\_Login...............................................................................................................................409 Figure 148: Sequence Diagram of UC-2\_Logout ............................................................................................................................409 Figure 149: Sequence Diagram of UC-3\_View the personal information............................................................................410 Figure 150: Sequence Diagram of UC-4\_Edit the personal information .............................................................................410 Figure 151: Sequence Diagram of UC-5\_Change password......................................................................................................410 Figure 152: Sequence Diagram of UC-6\_ Reset multiple account password .....................................................................411 Figure 153: Sequence Diagram of UC-7\_View account list.......................................................................................................411 Figure 154: Sequence Diagram of UC-8\_Search acoount...........................................................................................................411 Figure 155: Sequence Diagram of UC-9\_Create an account.....................................................................................................412 Figure 156: Sequence Diagram of UC-10\_Delete account.........................................................................................................412*

8/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 157: Sequence Diagram of UC-11\_View teacher list......................................................................................................412 Figure 158: Sequence Diagram of UC-12\_Search teacher.........................................................................................................413 Figure 159: Sequence Diagram of UC-13\_Add teacher...............................................................................................................413 Figure 160: Sequence Diagram of UC-14\_Edit teacher...............................................................................................................414 Figure 161: Sequence Diagram of UC-15\_Delete teacher..........................................................................................................414 Figure 162: Sequence Diagram of UC-16\_View class list...........................................................................................................414 Figure 163: Sequence Diagram of UC-17\_Search class..............................................................................................................415 Figure 164: Sequence Diagram of UC-18\_Edit information of the class.............................................................................415 Figure 165: Sequence Diagram of UC-19\_Change status of class..........................................................................................415 Figure 166: Sequence Diagram of UC-20\_Add new gifted class..............................................................................................416 Figure 167: Sequence Diagram of UC-21\_Add new class...........................................................................................................416 Figure 168: Sequence Diagram of UC-22\_Delete gifted class..................................................................................................417 Figure 169: Sequence Diagram of UC-23\_View the timetable of class.................................................................................417 Figure 170: Sequence Diagram of UC-24\_Search class timetable..........................................................................................417 Figure 171: Sequence Diagram of UC-25\_view the timetable of teacher............................................................................418 Figure 172: Sequence Diagram of UC-26\_Search teacher timetable ....................................................................................418 Figure 173: Sequence Diagram of UC-27\_Update new timetable...........................................................................................418 Figure 174: Sequence Diagram of UC-28\_View violation type list + UC-29\_View violation list............................419 Figure 175: Sequence Diagram of UC-30\_Edit violation type..................................................................................................419 Figure 176: Sequence Diagram of UC-31\_Add violation type ..................................................................................................420 Figure 177: Sequence Diagram of UC-32\_Delete violation type .............................................................................................420 Figure 178: Sequence Diagram of UC-33\_Edit violation............................................................................................................420 Figure 179: Sequence Diagram of UC-34\_Add violation............................................................................................................421 Figure 180: Sequence Diagram of UC-35\_Delete violation.......................................................................................................421 Figure 181: Sequence Diagram of UC-36\_View school year list.............................................................................................421 Figure 182: Sequence Diagram of UC-37\_Add new school year.............................................................................................422 Figure 183: Sequence Diagram of UC-38\_Edit information of school year.......................................................................422 Figure 184: Sequence Diagram of UC-39\_Delete school year..................................................................................................423 Figure 185: Sequence Diagram of UC-40\_View violation entering time .............................................................................423 Figure 186: Sequence Diagram of UC-41\_Add violation entering time ...............................................................................423 Figure 187: Sequence Diagram of UC-42\_Delete violation entering time ..........................................................................424 Figure 188: Sequence Diagram of UC-43\_View assign Red Star............................................................................................424 Figure 189: Sequence Diagram of UC-44\_Search assign Red Star........................................................................................424 Figure 190: Sequence Diagram of UC-45\_Download assign Red Star.................................................................................425 Figure 191: Sequence Diagram of UC-46\_Create assign Red Star........................................................................................425 Figure 192: Sequence Diagram of UC-47\_Delete assign Red Star.........................................................................................426 Figure 193: Sequence Diagram of UC-48\_View violation of class.........................................................................................426 Figure 194: Sequence Diagram of UC-49\_Search violation of class.....................................................................................426 Figure 195: Sequence Diagram of UC-50\_Add violation of class...........................................................................................427 Figure 196: Sequence Diagram of UC-51\_Edit violation of class...........................................................................................427 Figure 197: Sequence Diagram of UC-52\_View change request.............................................................................................428 Figure 198: Sequence Diagram of UC-53\_Search change request.........................................................................................428 Figure 199: Sequence Diagram of UC-54\_Accept change request .........................................................................................428 Figure 200: Sequence Diagram of UC-55\_Reject change request...........................................................................................429 Figure 201: Sequence Diagram of UC-56\_Cancel edit request................................................................................................429 Figure 202: Sequence Diagram of UC-57\_View violation history...........................................................................................429 Figure 203: Sequence Diagram of UC-58\_Search violation history ......................................................................................430 Figure 204: Sequence Diagram of UC-59\_View week rank........................................................................................................430 Figure 205: Sequence Diagram of UC-60\_Search week rank....................................................................................................430 Figure 206: Sequence Diagram of UC-61\_Download week rank ............................................................................................431 Figure 207: Sequence Diagram of UC-62\_View month rank.....................................................................................................431 Figure 208: Sequence Diagram of UC-63\_Search month rank.................................................................................................431 Figure 209: Sequence Diagram of UC-64\_Download month rank..........................................................................................432*

9/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 210: Sequence Diagram of UC-65\_View semester rank................................................................................................432 Figure 211: Sequence Diagram of UC-66\_ Search semester rank ..........................................................................................432 Figure 212: Sequence Diagram of UC-67\_Download semester rank.....................................................................................433 Figure 213: Sequence Diagram of UC-68\_ View year rank .......................................................................................................433 Figure 214: Sequence Diagram of UC-69\_Search year rank.....................................................................................................433 Figure 215: Sequence Diagram of UC-70\_Download year rank .............................................................................................434 Figure 216: Sequence Diagram of UC-71\_View school rank week history.........................................................................434 Figure 217: Sequence Diagram of UC-72\_View school rank month history ......................................................................434 Figure 218: Sequence Diagram of UC-73: View school rank semester history.................................................................435 Figure 219: Sequence Diagram of UC-74\_View school rank year history..........................................................................435 Figure 220: Sequence Diagram of UC-75\_ Create rank week...................................................................................................435 Figure 221: Sequence Diagram of UC-76\_Edit rank week .........................................................................................................436 Figure 222: Sequence Diagram of UC-77\_Update week rank...................................................................................................436 Figure 223: Sequence Diagram of UC-78\_Create rank month .................................................................................................436 Figure 224: Sequence Diagram of UC-79\_Edit rank month.......................................................................................................437 Figure 225: Sequence Diagram of UC-80\_Create rank semester............................................................................................437 Figure 226: Sequence Diagram of UC-81\_Edit rank semester..................................................................................................437 Figure 227: Sequence Diagram of UC-82\_Create rank year.....................................................................................................438 Figure 228: Sequence Diagram of UC-83\_Edit rank year..........................................................................................................438 Figure 229: Sequence Diagram of UC-84\_View home page......................................................................................................438 Figure 230: Sequence Diagram of UC-85\_Search newsletter...................................................................................................439 Figure 231: Sequence Diagram of UC-86\_View deltail newsletter.........................................................................................439 Figure 232: Sequence Diagram of UC-87\_Add a newsletter......................................................................................................439 Figure 233: Sequence Diagram of UC-88\_Edit newsletter.........................................................................................................440 Figure 234: Sequence Diagram of UC-89\_View newsletter request.......................................................................................440 Figure 235: Sequence Diagram of UC-90\_Search newsletter request...................................................................................440 Figure 236: Sequence Diagram of UC-91\_Change status of newsletter...............................................................................441 Figure 237: Five phases are considered in a genetic algorithm...............................................................................................443 Figure 238: Main function code...............................................................................................................................................................444 Figure 239: getFlag funtion code ............................................................................................................................................................445 Figure 240: CreatePopulation function code.....................................................................................................................................445 Figure 241: Evaluation function code ...................................................................................................................................................446 Figure 242: Print function code................................................................................................................................................................447 Figure 243: Selection function code .......................................................................................................................................................447 Figure 244: Mutation function code .......................................................................................................................................................447 Figure 245: Table Diagram........................................................................................................................................................................448 Figure 246: Screenflow for Module Manage Account ...................................................................................................................455 Figure 247: Mockup of Homepage..........................................................................................................................................................456 Figure 248: Mockup of Login....................................................................................................................................................................457 Figure 249: Mockup of Forgot Password............................................................................................................................................457 Figure 250: Mockup of Change Password ..........................................................................................................................................458 Figure 251: Mockup dialog of Change Password............................................................................................................................458 Figure 252: Mockup of Information of Account (1)........................................................................................................................459 Figure 253: Mockup of Information of Account (2)........................................................................................................................460 Figure 254: Mockup dialog of Information of Account................................................................................................................460 Figure 255: Mockup of Manage Account (1)......................................................................................................................................461 Figure 256: Mockup of Manage Account (2)......................................................................................................................................462 Figure 257: Mockup dialog confirm of Delete account.................................................................................................................463 Figure 258: Mockup dialog of Delete account ..................................................................................................................................463 Figure 259: Mockup of Reset password................................................................................................................................................463 Figure 260: Mockup dialog of Reset password .................................................................................................................................464 Figure 261: Mockup of Create Account - Step 1...............................................................................................................................464 Figure 262: Mockup of Create Account - Step 1 with is role Red Star or monitor class...............................................465*

10/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 263: Mockup of Create Account - Step 2 with role is red star or monitor class.................................................465 Figure 264: Mockup of Create Account - Step 2...............................................................................................................................466 Figure 265: Mockup dialog of Create Account.................................................................................................................................466 Figure 266: Screenflow for Module Manage Teacher...................................................................................................................467 Figure 267: Mockup of Manage Teacher (1)......................................................................................................................................468 Figure 268: Mockup of Manage Teacher (2)......................................................................................................................................469 Figure 269: Mockup dialog confirm of delete teacher...................................................................................................................469 Figure 270: Mockup dialog of delete teacher....................................................................................................................................469 Figure 271: Mockup of Create Teacher................................................................................................................................................470 Figure 272: Mockup dialog of Create Teacher.................................................................................................................................470 Figure 273: Mockup of Teacher Information.....................................................................................................................................471 Figure 274: Mockup dialog of Teacher Information ......................................................................................................................471 Figure 275: Screenflow for Module Manage Class.........................................................................................................................472 Figure 276: Mockup of Manage Class..................................................................................................................................................473 Figure 277: Mockup dialog confirm of delete class........................................................................................................................474 Figure 278: Mockup dialog of delete class..........................................................................................................................................474 Figure 279: Mockup of Create Class.....................................................................................................................................................474 Figure 280: Mockup dialog of Create Class (1)...............................................................................................................................475 Figure 281: Mockup dialog of Create Class (2)...............................................................................................................................475 Figure 282: Screenflow for Module Manage Timetable................................................................................................................476 Figure 283: Mockup of Timetable of Class.........................................................................................................................................477 Figure 284: Mockup of Timetable of Teacher....................................................................................................................................477 Figure 285: Mockup of Manage Timetable.........................................................................................................................................478 Figure 286: Mockup dialog of Manage Timetable (1)...................................................................................................................478 Figure 287: Mockup dialog of Manage Timetable (2)...................................................................................................................479 Figure 288: Screenflow for Module Manage Violation.................................................................................................................479 Figure 289: Screenflow for Module Manage School Year...........................................................................................................480 Figure 290: Screenflow for Module Manage Violation Entering Time..................................................................................480 Figure 291: Screenflow for Module Assign Red Star.....................................................................................................................481 Figure 292: Screenflow for Module Manage Emulation...............................................................................................................481 Figure 293: Screenflow for Module Manage School Rank ..........................................................................................................482 Figure 294: Screenflow for Module Manage Newsletter..............................................................................................................482 Figure 295: Agile Testing Process..........................................................................................................................................................484 Figure 296: Test Report of Unit Test Case..........................................................................................................................................489 Figure 297: Test Report of Unit Test Report (1)...............................................................................................................................490 Figure 298: Test Report of Unit Test Report (2)...............................................................................................................................490 Figure 299: Test Report of Integration Test Case............................................................................................................................491 Figure 300: Test Report of Integration Test Report........................................................................................................................491 Figure 301: Test Report of System Test Case.....................................................................................................................................492 Figure 302: Test Report of System Test Report.................................................................................................................................492 Figure 303: Bug log .......................................................................................................................................................................................493 Figure 304: Chart of evaluating the average convergence of number of generations in the algorithm.................494 Figure 305: Chart of evaluating the variation of the number of conflicts per generation ............................................494 Figure 306: User's Guide - Login (1)......................................................................................................................................................495 Figure 307: User's Guide - Login (2)......................................................................................................................................................496 Figure 308: User's Guide - Login (3)......................................................................................................................................................496 Figure 309: User's Guide - Logout (1)..................................................................................................................................................497 Figure 310: User's Guide - Logout (2)..................................................................................................................................................497 Figure 311: User's Guide - View the personal information........................................................................................................498 Figure 312: User's Guile - Edit personal information (1)...........................................................................................................499 Figure 313: User's Guile - Edit personal information (2)...........................................................................................................499 Figure 314: User's Guile - Edit personal information (3)...........................................................................................................500 Figure 315: User's Guile - Edit personal information (4)...........................................................................................................500*

11/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 316: User's Guide - Change password (1)............................................................................................................................501 Figure 317: User's Guide - Change password (2)............................................................................................................................501 Figure 318: User's Guide - Change password (3)............................................................................................................................502 Figure 319: User's Guide - Change password (4)............................................................................................................................502 Figure 320: User's Guide - View account list.....................................................................................................................................503 Figure 321: User's Guide - Search account (1).................................................................................................................................504 Figure 322: User's Guide - Search account (2).................................................................................................................................504 Figure 323: User's Guide - Reset multiple password (1).............................................................................................................505 Figure 324: User's Guide - Reset multiple password (2).............................................................................................................505 Figure 325: User's Guide - Delete account (1)..................................................................................................................................506 Figure 326: User's Guide - Delete account (2)..................................................................................................................................506 Figure 327: User's Guide - Create account (1).................................................................................................................................507 Figure 328: User's Guide - Create account (2).................................................................................................................................507 Figure 329: User's Guide - Create account (3).................................................................................................................................508 Figure 330: User's Guide - Create account (4).................................................................................................................................508 Figure 331: User's Guide - Create account (5).................................................................................................................................509 Figure 332: User's Guide - View teacher list......................................................................................................................................509 Figure 333: User's Guide - Search teacher (1).................................................................................................................................510 Figure 334: User's Guide - Search teacher (2).................................................................................................................................510 Figure 335: User's Guide - Add teacher (1)........................................................................................................................................511 Figure 336: User's Guide - Add teacher (2)........................................................................................................................................511 Figure 337: User's Guide - Add teacher (3)........................................................................................................................................512 Figure 338: User's Guide - Add teacher (4)........................................................................................................................................512 Figure 339: User's Guide - Edit teacher (1).......................................................................................................................................513 Figure 340: User's Guide - Edit teacher (2).......................................................................................................................................513 Figure 341: User's Guide - Edit teacher (3).......................................................................................................................................513 Figure 342: User's Guide - Edit teacher (4).......................................................................................................................................514 Figure 343: User's Guide - Delete teacher (1)...................................................................................................................................514 Figure 344: User's Guide - Delete teacher (2)...................................................................................................................................515 Figure 345: User's Guide - Delete teacher (3)...................................................................................................................................515 Figure 346: User's Guide - View class list............................................................................................................................................516 Figure 347: User's Guide - Search class (1)........................................................................................................................................517 Figure 348: User's Guide - Search class (2)........................................................................................................................................517 Figure 349: User's Guide - Edit information of class (1).............................................................................................................518 Figure 350: User's Guide - Edit information of class (2).............................................................................................................518 Figure 351: User's Guide - Edit information of class (3).............................................................................................................519 Figure 352: User's Guide - Edit information of class (4).............................................................................................................519 Figure 353: User's Guide - Change status of class (1)...................................................................................................................520 Figure 354: User's Guide - Change status of class (2)...................................................................................................................520 Figure 355: User's Guide - Change status of class (3)...................................................................................................................520 Figure 356: User's Guide - Add new class (1)....................................................................................................................................521 Figure 357: User's Guide - Add new class (2)....................................................................................................................................521 Figure 358: User's Guide - Add new class (3)....................................................................................................................................522 Figure 359: User's Guide - Add new class (4)....................................................................................................................................522 Figure 360: User's Guide - Add new gifted class (1)......................................................................................................................523 Figure 361: User's Guide - Add new gifted class (2)......................................................................................................................523 Figure 362: User's Guide - Add new gifted class (3)......................................................................................................................524 Figure 363: User's Guide - Add new gifted class (4)......................................................................................................................524 Figure 364: User's Guide - Delete gifted class (1)...........................................................................................................................524 Figure 365: User's Guide - Delete gifted class (2)...........................................................................................................................525 Figure 366: User's Guide - Delete gifted class (3)...........................................................................................................................525 Figure 367: User's Guide - Delete gifted class (4)...........................................................................................................................525 Figure 368: User's Guide - View the timetable of class................................................................................................................526*

12/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 369: User's Guide - View the timetable of class................................................................................................................526 Figure 370: User's Guide - Search the timetable of class (1)....................................................................................................527 Figure 371: User's Guide - Search the timetable of class (2)....................................................................................................527 Figure 372: User's Guide - View the timetable of teachers........................................................................................................528 Figure 373: User's Guide - View the timetable of teachers........................................................................................................528 Figure 374: User's Guide - Search the timetable of teachers (1)............................................................................................529 Figure 375: User's Guide - Search the timetable of teachers (2)............................................................................................529 Figure 376: User's Guide - Update new timetable (1)..................................................................................................................530 Figure 377: User's Guide - Update new timetable (2)..................................................................................................................530 Figure 378: User's Guide - Update new timetable (3)..................................................................................................................530 Figure 379: User's Guide - View violation type list and violation list (1)...........................................................................531 Figure 380: User's Guide - View violation type list and violation list (2)...........................................................................531 Figure 381: User's Guide - View violation type list and violation list (3)...........................................................................532 Figure 382: User's Guide - Add violation type (1)..........................................................................................................................532 Figure 383: User's Guide - Add violation type (2)..........................................................................................................................533 Figure 384: User's Guide - Add violation type (3)..........................................................................................................................533 Figure 385: User's Guide - Add violation (1).....................................................................................................................................534 Figure 386: User's Guide - Add violation (2).....................................................................................................................................534 Figure 387: User's Guide - Add violation (3).....................................................................................................................................534 Figure 388: User's Guide - Edit violation type (1)..........................................................................................................................535 Figure 389: User's Guide - Edit violation type (2)..........................................................................................................................535 Figure 390: User's Guide - Edit violation type (3)..........................................................................................................................535 Figure 391: User's Guide - Edit violation (1).....................................................................................................................................536 Figure 392: User's Guide - Edit violation (2).....................................................................................................................................536 Figure 393: User's Guide - Edit violation (3).....................................................................................................................................537 Figure 394: User's Guide - Delete violation type (1).....................................................................................................................537 Figure 395: User's Guide - Delete violation type (2).....................................................................................................................537 Figure 396: User's Guide - Delete violation type (3).....................................................................................................................538 Figure 397: User's Guide - Delete violation (1)................................................................................................................................538 Figure 398: User's Guide - Delete violation (2)................................................................................................................................538 Figure 399: User's Guide - Delete violation (3)................................................................................................................................539 Figure 400: User's Guide - View school year list..............................................................................................................................539 Figure 401: User's Guide - Add new school year (1)......................................................................................................................540 Figure 402: User's Guide - Add new school year (2)......................................................................................................................540 Figure 403: User's Guide - Add new school year (3)......................................................................................................................540 Figure 404: User's Guide - Add new school year (4)......................................................................................................................541 Figure 405: User's Guide - Edit information of school year (1)...............................................................................................541 Figure 406: User's Guide - Edit information of school year (2)...............................................................................................542 Figure 407: User's Guide - Delete school year (1)..........................................................................................................................542 Figure 408: User's Guide - Delete school year (2)..........................................................................................................................542 Figure 409: User's Guide - Delete school year (3)..........................................................................................................................543 Figure 410: User's Guide - View violation entering time ............................................................................................................543 Figure 411: User's Guide - Add violation entering time (1)......................................................................................................544 Figure 412: User's Guide - Add violation entering time (2)......................................................................................................544 Figure 413: User's Guide - Add violation entering time (3)......................................................................................................545 Figure 414: User's Guide - Delete violation entering time (1).................................................................................................545 Figure 415: User's Guide - Delete violation entering time (2).................................................................................................546 Figure 416: User's Guide - Delete violation entering time (3).................................................................................................546 Figure 417: User's Guide - View assign Red Star.............................................................................................................................546 Figure 418: User's Guide - View assign Red Star.............................................................................................................................547 Figure 419: User's Guide - Search assign Red Star (1).................................................................................................................547 Figure 420: User's Guide - Search assign Red Star (2).................................................................................................................548 Figure 421: User's Guide - View assign Red Star.............................................................................................................................548*

13/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 422: User's Guide - Download assign Red Star (1).........................................................................................................549 Figure 423: User's Guide - Download assign Red Star (2).........................................................................................................549 Figure 424: User's Guide - Create assign Red Star (1).................................................................................................................550 Figure 425: User's Guide - Create assign Red Star (2).................................................................................................................550 Figure 426: User's Guide - Create assign Red Star (3).................................................................................................................550 Figure 427: User's Guide - Delete assign Red Star (1)..................................................................................................................551 Figure 428: User's Guide - Delete assign Red Star (2)..................................................................................................................551 Figure 429: User's Guide - Delete assign Red Star (3)..................................................................................................................551 Figure 430: User's Guide - Delete assign Red Star (4)..................................................................................................................552 Figure 431: User's Guide - View list of violations by day ............................................................................................................552 Figure 432: User's Guide - View list of violations by day ............................................................................................................553 Figure 433: User's Guide - Search list of violations by day ........................................................................................................553 Figure 434: User's Guide - Add violation of class (1)....................................................................................................................554 Figure 435: User's Guide - Add violation of class (2)....................................................................................................................554 Figure 436: User's Guide - Add violation of class (3)....................................................................................................................555 Figure 437: User's Guide - Edit violation of class (1)....................................................................................................................555 Figure 438: User's Guide - Edit violation of class (2)....................................................................................................................556 Figure 439: User's Guide - Edit violation of class (3)....................................................................................................................556 Figure 440: User's Guide - Edit violation of class (4)....................................................................................................................556 Figure 441: User's Guide - View change request.............................................................................................................................557 Figure 442: User's Guide - Search change request.........................................................................................................................557 Figure 443: User's Guide - Accept change request (1).................................................................................................................558 Figure 444: User's Guide - Accept change request (2).................................................................................................................558 Figure 445: User's Guide - Accept change request (3).................................................................................................................558 Figure 446: User's Guide - Reject change request (1)..................................................................................................................559 Figure 447: User's Guide - Reject change request (2)..................................................................................................................559 Figure 448: User's Guide - Reject change request (3)..................................................................................................................560 Figure 449: User's Guide - Cancel edit request (1).........................................................................................................................560 Figure 450: User's Guide - Cancel edit request (2).........................................................................................................................560 Figure 451: User's Guide - Cancel edit request (3).........................................................................................................................561 Figure 452: User's Guide - View violation history ..........................................................................................................................561 Figure 453: User's Guide - View violation history ..........................................................................................................................562 Figure 454: User's Guide - Search violation history ......................................................................................................................562 Figure 455: User's Guide - View school rank by week ..................................................................................................................563 Figure 456: User's Guide - Search school rank by week (1)......................................................................................................563 Figure 457: User's Guide - Search school rank by week (2)......................................................................................................564 Figure 458: User's Guide - Download school rank by week (1)...............................................................................................564 Figure 459: User's Guide - Download school rank by week (2)...............................................................................................565 Figure 460: User's Guide - View history of school rank by week (1).....................................................................................565 Figure 461: User's Guide - View history of school rank by week (2).....................................................................................566 Figure 462: User's Guide - Create school rank by week (1).......................................................................................................566 Figure 463: User's Guide - Create school rank by week (2).......................................................................................................567 Figure 464: User's Guide - Create school rank by week (3).......................................................................................................567 Figure 465: User's Guide - Edit school rank by week (1)............................................................................................................567 Figure 466: User's Guide - Edit school rank by week (2)............................................................................................................568 Figure 467: User's Guide - Edit school rank by week (3)............................................................................................................568 Figure 468: User's Guide - Update week rank (1)..........................................................................................................................568 Figure 469: User's Guide - Update week rank (2)..........................................................................................................................569 Figure 470: User's Guide - Update week rank (3)..........................................................................................................................569 Figure 471: User's Guide - View school newsletters......................................................................................................................570 Figure 472: User's Guide - Search school newsletters..................................................................................................................571 Figure 473: User's Guide - View school newsletters (1)..............................................................................................................572 Figure 474: User's Guide - View school newsletters (2)..............................................................................................................573*

14/579

HVT Digital Transformation – Final Report v.1.1.9

*Figure 475: User's Guide - Add a newsletter (1).............................................................................................................................573 Figure 476: User's Guide - Add a newsletter (2).............................................................................................................................574 Figure 477: User's Guide - Add a newsletter (3).............................................................................................................................575 Figure 478: User's Guide - Add a newsletter (4).............................................................................................................................575 Figure 479: User's Guide - Edit newsletter (1).................................................................................................................................576 Figure 480: User's Guide - Edit newsletter (2).................................................................................................................................576 Figure 481: User's Guide - Edit newsletter (3).................................................................................................................................577 Figure 482: User's Guide - Edit newsletter request (1)................................................................................................................577 Figure 483: User's Guide - Edit newsletter request (2)................................................................................................................577 Figure 484: User's Guide - Search newsletter request..................................................................................................................578 Figure 485: User's Guide - Change status of newsletter (1)......................................................................................................578 Figure 486: User's Guide - Change status of newsletter (2)......................................................................................................579 Figure 487: User's Guide - Change status of newsletter (3)......................................................................................................579 Figure 488: User's Guide - Change status of newsletter (4)......................................................................................................579*

15/579

HVT Digital Transformation – Final Report v.1.1.9

**CHAPTER 1: INTRODUCTION**

This chapter provides an overview of the HVT Digital Transformation project. This document includes project information, supervisor, project team members, the overview of existing systems, the problems and solution of the project, a brief description of our expected application, and some critical assumptions, constraints. In the end, it will be some out of the scope of the project.

**1. PROJECT INFORMATION**

❖ **Project name:** HVT Digital Transformation

❖ **Project code:** HVT Digital Transformation

❖ **Project group name:** SWP490\_G24

❖ **Project type:** Web Application

❖ **Project category:** New Development

❖ **Scrum master:** Vu Bao Yen

❖ **Timeline:** From 18th May 2020 to 28th Aug 2020

**2. PROJECT TEAM**

**2.1. Supervisor**

**Full name Phone**

**number Email Title**

Supervisor Tran Binh Duong 0936168165 Duongtb@fe.edu.vn Lecturer Supervisor Vuong Thanh Trung 0916819984 Trungvt130584@gmail.com Customer Supervisor Nguyen Tien Dung 0911228595 Dungnthvt@gmail.com Customer

**2.2. Team members**

**No. Full name Student ID**

**Number Email Role in**

**Phone**

**Group**

1 Vu Bao Yen SE05610 0354306555 Yenvbse05610@fpt.edu.vn Leader 2 Pham Trong Kim SE05423 0967191052 Kimptse05423@fpt.edu.vn Member 3 Nguyen Tung Lam SE05790 0347059998 Lamntse05790@fpt.edu.vn Member 4 Nguyen Thi Kim Loan SE05636 0941687957 Loanntkse05636@fpt.edu.vn Member

16/579

HVT Digital Transformation – Final Report v.1.1.9

**3. INITIAL IDEA**

**3.1. Background**

Hoang Van Thu gifted high school is one of the top schools in Hoa Binh city. The school has been established for nearly 75 years and has made great contributions to the cause of education by helping 95% of ethnic minorities eradicate illiteracy. Not only that, the school has also achieved many great achievements, such as from 2002-

2013, the school had 488 national excellent student prizes in one class, thus creating a tradition of studious learning in Hoa Binh province. Thanks to the quality of teaching and learning, the school has attracted students of the whole province. Currently, the school has more than 1200 students.

With the large number of students, the management task becomes difficult. The management of emulation grades at the school is done manually from jobs such as recording violations in each class, recording violations at the school gate, and summarizing the emulation points. Besides, traditional activities as well as club activities have not been communicated to everyone. Along with that, when there is a change in the schedule, it is difficult for teachers and students to update promptly. The school has not the solution to overcome the problems yet.

Today, Technology 4.0 is the trend of the whole world. It affects our life, economy, social science... In that situation, manual work has become obsolete. Instead, digitization makes it easy, convenient and saves time and resources. Therefore, SWP490\_G24 project team decided to build a website to help the school overcome these difficulties.

**3.2. Digital transformation phase**

The digital transformation has six phases. Include:

1. COMPUTERISATION

2. CONNECTIVITY

3. VISIBILITY

4. TRANSPARENCY

5. PREDICTIVE

6. ADAPTABLE

The digital transformation phase at this school is computerization. The school just have the basis for digitization and different information technologies were used separately from the school. Computer software is mainly used to perform repetitive tasks more effectively.

17/579

HVT Digital Transformation – Final Report v.1.1.9

**3.3. Problem**

There is some problem defined:

- Students are having trouble way to evaluate the emulation grade like take 15 minutes to summit the paper of grade for teachers, take 20 minutes to write each violation of classes.

- Teachers can not follow and monitor closely with the Red Star team. For example, the Red Star team can change the final grade before they summit grades for teachers and implicit agreement to fix their grades.

- The emulation grade calculation is done manually that use students to evaluate.

- The school have not the complete process for emulation grade yet. The responsibility of each role is not clear and can make mistake when they evaluate.

- The existing website of school have not diversity information about the internal activities and the club activities and the information can not deliver to teachers and students quickly.

- The timetable of the school is offline for student and it’s general for all teachers. Students and teachers waste their time when using complex ways to get timetable like the monitor has a handwritten timetable by getting it at the bulletin board and then shares with classmates, teachers get the excel file in the Facebook group and find their schedule in this file.

- This school is wasting time to assign Red Star for classes. A teacher will create an excel table and fill each element to assign Red Star for each class and there are some constraints that assigning must be followed.

**3.4. Existing Products**

**3.4.1. Website http://chuyenhoangvanthu.hoabinh.edu.vn**

Website of Hoang Van Thu Gifted High School is the school portal. The website provides basic information about the school, its timetables, teaching resources, and school activities.

**Functions:**

- Post information, plan activities

- Search teaching resources

- Look up admission information

- Post the school's decision

- Look up information for teachers and delegations

- Review information and biography of the school

18/579

HVT Digital Transformation – Final Report v.1.1.9

**Some screenshots:**

*****Figure 1: Screenshot of website 1 Figure 2: Screenshot of website 2*

*Figure 3: Screenshot of website 3 Figure 4: Screenshot of website 4*

**Pros:**

- Interface design is simple

- Search documents quickly

**Cons:**

- The document is not updated

- Difficult to use, difficult to post new articles

- Students and teachers do not use the site because the information is not updated

- Only watch function

19/579

HVT Digital Transformation – Final Report v.1.1.9

**3.4.2. Timetable creation software**

**Functions:**

- Creating timetables:

+ Input methods: the system will show the form to user fill the information manually are subject, class, grade and teacher.



*Figure 5: Enter the subject list in Timetable creation software*

*Figure 6: Enter the class list in Timetable creation software*

20/579

HVT Digital Transformation – Final Report v.1.1.9 

*Figure 7: Enter the teacher list in Timetable creation software*

*Figure 8: Enter the grade list in Timetable creation software*

21/579

HVT Digital Transformation – Final Report v.1.1.9

+ The system output are HTML folder and Excel file.

*Figure 9: Timetable of all class as an Excel file*

*Figure 10: Timetable of all teachers as an Excel file*

22/579

HVT Digital Transformation – Final Report v.1.1.9 

*Figure 11: Morning timetable of all class as HTML folder*

*Figure 12: Timetable of teacher as HTML folder*

**Relationship with current system:**

- Provide timetables for the current system.

**3.5. Solution**

In this section, let we explain why using website would be a potential solution in Hoang Van Thu Gifted High School:

- Help students easily in emulation grading.

- Teachers can manage the activities of the Red Star team well.

- Aggregate and calculate the emulation points quickly.

- Develop a complete process for emulation grading.

- Easy to propagate the school and club activities.

- Help students and teachers to follow easily when schedules change.

23/579

HVT Digital Transformation – Final Report v.1.1.9

**3.6. System Proposals**

Reviewing and analyzing the problem show that in the system there are Red Star team, Club Leader, Monitor, Summarize Group, Admin, Schedule Manager and All Users who use the system without login.

**3.6.1. All users**

All users (no need to login) can use the following functions:

- Log in.

- View school newsletters.

- Search school newsletters by title

- View/ search the timetable of classes.

- View/ search the timetable of teachers.

- View/ search list of violations by day.

- View/ search violation history.

- View violation type list/ violation list.

- View/search violation history.

- View violation entering time.

- View/ search/ download assign Red Star.

- View school week/month/semester/year rank.

- View school week/month/semester/year rank history.

- Search school week/month/semester/year rank by condition.

- Download school week/month/semester/year rank.

**3.6.2. Red Star team**

In addition to the functions that all users can use, Red Star team can use the following functions:

- Logout.

- View personal information.

- Add violation of a class.

- Edit violation of a class.

- Edit the personal information.

- Change password.

**3.6.3. Club Leader**

In addition to the functions that all users can use, Club Leader can use the following functions:

- Logout.

- View personal information.

- Edit the personal information.

- Change password.

- Search newsletter request.

24/579

HVT Digital Transformation – Final Report v.1.1.9

- Create newsletter request.

- Edit newsletter request.

**3.6.4. Monitor**

In addition to the functions that all users can use, Monitor can use the following functions:

- Logout.

- View personal information.

- Edit the personal information.

- Change password.

- Search newsletter request.

- Add newsletter request.

- Edit newsletter request.

- Edit violation of a class.

- View change request.

**3.6.5. Summarize Group**

In addition to the functions that all users can use, Summarize Group can use the following functions:

- Logout.

- Change password.

- View personal information.

- Edit the personal information.

- Add violation of a class.

- Edit violation of a class.

**3.6.6. Admin**

In addition to the functions that all users can use, Admin can use the following functions:

- Logout.

- View the personal information. - Edit the personal information. - Change password.

- Reset multiple account password. - View account list.

- Search account.

- Create an account.

- Delete account.

- View teacher list.

- Search teacher.

- Add teacher.

- Add violation entering time. - Delete violation entering time. - Create assign Red Star. - Delete assign Red Star. - View violation of a class. - Search violation of a class. - Add violation of a class. - Edit violation of a class. - View change request.

- Search change request. - Accept change request. - Reject change request.

25/579

HVT Digital Transformation – Final Report v.1.1.9

- Edit teacher.

- Delete teacher.

- View class list.

- Search class.

- Edit information of the class. - Change status of class.

- Add new gifted class.

- Delete gifted class.

- Add new class.

- Update new timetable.

- Edit violation type.

- Add violation type.

- Delete violation type.

- Edit violation.

- Add violation.

- Delete violation.

- View school year list.

- Add new school year.

**3.6.7. Schedule Manager**

- Cancel edit request.

- Create rank week.

- Edit rank week.

- Update week rank.

- Create rank month.

- Edit rank month.

- Create rank semester.

- Edit rank semester.

- Create rank year.

- Edit rank year.

- Add a newsletter.

- Edit newsletter.

- View newsletter request. - Search newsletter request. - Change status of newsletter request.

- Edit information of school year. - Delete school year.

In addition to the functions that all users can use, Schedule Manager can use the following functions:

- Logout.

- View personal information.

- Edit the personal information.

- Change password.

- Update new timetable.

26/579

HVT Digital Transformation – Final Report v.1.1.9

**CHAPTER 2: PROJECT MANAGEMENT PLAN**

**1. INTRODUCTION**

**1.1. Document Description**

This document is to provide a comprehensive baseline of how the project will be run, what has to be achieved by the project, how it is to be achieved, who will be involved, how it will be reported and measured, how the information will be communicated, and how the risk should be defined.

**1.2. Document Scope**

This document consists of our project overview. In the next, we will discuss the project process which includes the model, lifecycle, and responsibilities of each stakeholder in section 4. In section 5, we will show the tool and the infrastructures that will necessary in this project for coding, managing, and developing. Besides, the schedule of the project will be shown through detailed work with a specific date. In the final, we will define the communication management plan and project risk.

**2. PROJECT OVERVIEW**

**2.1. Project description**

In this project, we will develop an Web application that supports HVT Gifted High School in managing the emulation grade, school activities and timetable. Users can use this application to follow the emulation grade of all classes. Besides, users can also follow school activities. In addition, users will see the online timetable when it changes. This website will improve and complete the process of evaluating the emulation grades. Therefore, users can follow and look at the emulation grades quickly. Students and teachers can have an update on school activities daily and timetables. The Application will be designed so that users have to do least but receive the best result.

**2.2. Project Scope**

This project covers all processes, from planning, requirement specification, design, development, to testing.

Project team will develop a Web Application for users to manage the emulation grade, activities and timetable of HVT Gifted High School.

**2.2.1. Functional**

- Application allows all users to view school activities, the schedule of all classes and teachers, view violation, view violation history, search violation history,

27/579

HVT Digital Transformation – Final Report v.1.1.9

emulation scores of classes and view rank of school. All users except students and teachers must login to the application to use other functions in application. - Club leaders and monitors can send a request to post media.

- Monitors have requested to change violations of their class daily. - Summarize Group can enter emulation grades of all classes and edit violation of class in entering time and current day.

- Admins see their own timetable. They have been authorized to change the information of all accounts (create, edit, view, delete password). Besides, they import and edit emulation grades of all classes. Admins can set a deadline for importing violations, censoring and deleting newsletters.

- The schedule manager views personal information. Otherwise they can edit information and update the timetable of school.

- All accounts can log out from the system.

**2.2.2. Non-functional**

The Application must be designed for user’s convenience. It should require internet access to run. Interface design should be good looking and easy to understand. Time delay for system processing must be optimized. The interface performance of the system can run almost any smartphone. The system develops to maintain and extend easily.

**2.3. Standard Objectives**

- This project must be finished no later than 28/08/2020.

- The final Application covers 100% of requirements.

- The 4 team members give the best effort to complete the project.

**3. PROJECT TEAM**

**3.1. Software Process Model**

*****Figure 13: Scrum model*

In this project, we apply the Scum model as a development process model.

28/579

HVT Digital Transformation – Final Report v.1.1.9

**3.2. Project Lifecycle**

In this project, we apply the Scum model as a development process model. Scrum lifecycle is a number of consecutive steps and iterative stages that should be performed during the realization of any Scrum project. The iterative approach is the main principle of Scrum lifecycle. The work on a Scrum project is subdivided into 5 faces including Initiating segment and 4 sprints. The project develops from one sprint to another until the final product is ready. Each sprint is subdivided into several consecutive stages that it must pass from the beginning till the end.

The first step of the project is the stage of gathering necessary information about the future product. We are the person who contacts the customer to understand his vision of the future software. Gathering user stories is also one of his responsibilities. After all user stories are collected and all the customer’s wishes are considered, they are prioritized in a list that is called a product backlog. It is the main document of the project.

After the prioritization of the product backlog items, they are turned into tasks and divided into several sprints. The team makes it during the sprint planning meetings. The main goal of each meeting is to create a sprint backlog. It is a document that contains all tasks for a certain sprint. After the sprint is finished the work of the team will be estimated in accordance with the fulfillment of the sprint backlog requirements.

The next step in the Scrum lifecycle is the process of sprint execution. It includes a consequent performance of all sprint tasks and everyday evaluation of workflow. The progress of the sprint backlog requirements is evaluated during the daily Scrums – the team gatherings where all the positive and negative work issues are discussed.

After the sprint comes to its end, all members of the team participate in the sprint review and the sprint retrospectives. These gatherings help to find out what went wrong during the sprint.

The final step of every sprint is the stage of product estimation. The product is evaluated in accordance with the team’s definition of “Done” and provided to the customer to obtain his feedback. Then a new sprint starts, and the cycle repeats.

29/579

HVT Digital Transformation – Final Report v.1.1.9

**3.3. Roles and Responsibilities**

*****Figure 14: Project Organization Structure*

**Role Full Name Responsibility** - Give instruction for project team

**Supervisor** Tran Binh Duong

**Scrum**

**master - PM** Vu Bao Yen **PO (Product**

- Verify deliverables

- Supervise project team’s status

- Ensure Project process is followed - Ensure a reasonable interaction between PO, Team and Supervisor

- Protect and motivate Team

- Support in organizing activities (such as meetings, infrastructure, etc.)

- Support Team to focus on work and achieve current project goals

- Working with PO to understand requirements, propose solutions, request to change stories

- Support activities such as Team building, developing skills for members, building feedback, etc.

- Detect and solve problems

- Reviewing Product Backlog

**Owner) - Main**

**Customer**

Nguyen Tien Dung

- Regularly monitor the construction of user stories

- Review the functions given in each version

30/579

HVT Digital Transformation – Final Report v.1.1.9

Vu Bao Yen - Understand requirements, analysis, design, product coding

- Understand and follow the project process

**Develop team**

Pham Trong Kim

Nguyen Tung Lam

Nguyen Thi Kim Loan

- Attend Kick off, Sprint Planning, Sprint Review, Daily Scrum Meeting

- Get the job, estimate and be responsible for your work for the quality and deadline - Design test and execution test

- Bug fixes and product improvement contributions

**4. TOOLS AND INFRASTRUCTURES**

**4.1. Hardware**

- Personal computer for coding and testing with minimum configuration of 4GB RAM, Intel core 2 Duo.

- Smartphones run on web browsers.

- Internet network connection.

**4.2. Software**

**Category Software Name Version Operating System** Microsoft Windows 10 Professional Microsoft Word 2019

**Office Tools**

**Management Tool**

Microsoft Excel 2019 Microsoft Powerpoint 2019 Trello

Google Drive

Facebook

**Design Tool** https://app.lucidchart.com

**Development Tool** IntelliJ IDEA 2020.1.2 **Database Tool** SQL Server 2017

**Source Code**

**Management Tool**

Source Tree 3.3.8 Github.com

31/579

HVT Digital Transformation – Final Report v.1.1.9

**5. SCHEDULES**

**5.1. Detail Schedules**

*****Figure 15: Schedule for Initiating Phase*

32/579

HVT Digital Transformation – Final Report v.1.1.9



*Figure 16: Schedule for Sprint 1*

33/579

HVT Digital Transformation – Final Report v.1.1.9



*Figure 17: Schedule for Sprint 2*

34/579

HVT Digital Transformation – Final Report v.1.1.9



*Figure 18: Schedule for Sprint 3*

35/579

HVT Digital Transformation – Final Report v.1.1.9



*Figure 19: Schedule for Sprint 4*

36/579

HVT Digital Transformation – Final Report v.1.1.9

**5.2. Milestones and Deliverable**

**No. Milestones Deliverable Date 1** Kick-off first Meeting Topic of project 19/05/2020

**2**Complete Initiating Stage

**3**Sprint Planning meeting

Report 1 - Introduction

Project summary 04/06/2020

for sprint 1 Detail plan of sprint 1 05/06/2020 Product Backlog

Report 2 - project management

**4** Complete Sprint 1 **5**Sprint Planning meeting

plan

Report 3 - SRS

Database

Detail Design for Module 1,2,3,4

17/06/2020

for sprint 2 Detail plan of sprint 2 18/06/2020 Complete Module 1,2,3,4

**6** Complete Sprint 2 **7**Sprint Planning meeting

Test plan

Detail Design for Module 5,6,7,8,9,10

08/07/2020

for sprint 3 Detail plan of sprint 3 09/07/2020 Complete Module 5,6,7,8,9,10

**8** Complete Sprint 3 **9**Sprint Planning meeting

Unit Test Report for Module 1,2,3,4

Detail Design for Module 11

26/07/2020

for sprint 4 Detail plan of sprint 4 27/07/2020 Unit Test Report for Module

5,6,7,8,9,10

**10** Complete Sprint 4 **11** Submit final report of

Complete Module 11 Report 4

Report 5

Report 6

25/08/2020

Testing Final Report 31/8/2020 **12** Presentation Completed Project 10/9/2020

37/579

HVT Digital Transformation – Final Report v.1.1.9

**6. COMMUNICATION MANAGEMENT**

**6.1. Stakeholders and Contacts**

**Name Title Role Contacts**

Tran Binh Duong Mr. Supervisor duongtb@fe.edu.vn (84) 936-168-165

Vuong Thanh Trung Mr. Customer trungvt130584@gmail.com (84) 916-819-984

Nguyen Tien Dung Mr. Customer (84) 911-228-595 Vu Bao Yen Mrs. Leader yenvbse05610@fpt.edu.vn (84) 354-306-555

Pham Trong Kim Mr. Member kimptse05423@fpt.edu.vn (84) 967-191-052

Nguyen Tung Lam Mr. Member lamntse05790@fpt.edu.vn (84) 347-059-998

Nguyen Thi Kim Loan Mrs. Member loanntkse05636@fpt.edu.vn (84) 941-687-957

**6.2. Communication Management Approach**

Scrum master communicates frequently to ensure the progress of each member’s work every day in daily scrum meetings. Scum master report honestly to the Supervisor once a week so that the Supervisor can track the team’s work and give support/advice as needed.

All requests for change or proposal of new ideals must be discussed with the member, PO, and scrum master. If the project team agrees to change, Scrum master must discuss it with the supervisor after that. Once the change is approved, the scrum master will update the plan.

**6.3. Communication Requirements**

The Scrum master will communicate with the Supervisor in order to determine his preferred frequency and time of communication.

As all project team members still take part in classes while doing projects, Scrum master should communicate to understand their schedule, and therefore specify appropriate communication plans for the team.

**6.4. Communication Method and Technologies**

- The project team will have a sprint planning meeting to define the planning that the project will do for the sprint at the beginning of the sprint.

- We have a daily meeting that lasting 15 minutes to answer some questions like What did yesterday do? What will you do today? Are there any problems?

38/579

HVT Digital Transformation – Final Report v.1.1.9

- Create a Facebook private group for team members to discuss and share informal information and activity. This would be a place for members to communicate freely, and therefore would help in strengthen relationship between members. - Use Google docs to share documents.

- Public weekly reports of team members in Google docs to keep them writing reports. This will help scrum masters in tracking work of team members, and also help team members understand the progress of others.

- Update Work schedule before weekly meeting with Supervisor. - Manage the plan and task above Trello tool.

**7. RISK MANAGEMENT**

**7.1. Risk Management Approach**

The approach to managing risks for this project is the process by which the project team identifies and ranks the various risks. The most likely and high impact risks will be added to the risk register and will be delivered to all team members, to ensure that every member perceives these potential risks. The scrum master must pay attention to all items in the risk register during the project and take appropriate action when risk is triggered. Upon the completion of the project, the scrum master will analyze each risk as well as the management process. Based on this analysis, the scrum master will identify any improvements that can be made to the risk management process and capture these improvements as a part of the lessons learned.

The approach to managing risks for this project is the process by which the project team identifies in every sprint meeting. Scrum master and team members will analyze each risk as well as find the solution after the sprint meeting end up. The scrum master has responsibilities to manage all risks that be defined. The team members will identify any improvements that can be made to the risk management process and capture these improvements as a part of the lessons learned in the sprint retrospection meeting after each sprint.

**7.2. Risk Identification**

Risk identification will be conducted in the sprint meeting. The risks will be written down by a team member when all team members answer the question that is "Are there any problems?". All team members don't need to get detail on how to resolve the risk in the sprint meeting.

Otherwise, the project team can define the project risk in each sprint. The risk will appear when the project is running.

Besides, the project team will review other capstone projects in order to determine the most common risks and the strategies used to mitigate those risks.

39/579

HVT Digital Transformation – Final Report v.1.1.9

**7.3. Risk Qualification and Prioritization**

In order to determine the severity of the risks identified by the project team, a probability and impact factor will be assigned to each risk. Scrum master will prioritize risks based on their probability and impact. Finally, the scrum master will create a probability – impact matrix.

**7.4. Risk Monitoring**

Risk monitoring will be a continuous process throughout the project. The avoidance plan should be taken care of from the start of the project. In case a risk is about to happen, the Scrum master and the team members will apply a contingency plan to prevent risk. If the risk already happens, Scrum master and the team members will apply to the fall back plan to minimize the impact.

40/579

HVT Digital Transformation – Final Report v.1.1.9

**7.5. Risk Register**

**7.5.1. Risk description of all project**

**No. Risk Name Description Category Route cause Probability ImpactRisk response Risk Contingency Risk Mitigation**

- Do well at the training

**R1**

Lack of skills and ability for a specified work

Team members may be unable to complete work because they have trouble in how to do. Therefore,

project may be over deadline

Team member may disagree with each

Human

Team members have not studied or not enough experienced

work.

Unclear

requirement

High High

together.

- Find materials and self study.

- The scrum master should understand the ability of each team member and assign the right work for the right person.

- Clear requirement.

- Assign more team members to support or to do the task.

- Ask for the support of external others.

- Negotiate to deal with

**R2** Team member may conflict

**R3** Requirement may change

others and refuse to work. Therefore, project may not enough member to complete the work

The scope may change, unplanned requirements may get added.

Therefore, project can be over

Human

Requirement

specification. Team members do not unify on solutions when problems occur.

Request from Supervisor or customer for new function, or to change

requirement

Medium High Medium High

- Pay attention to team building activities.

- Organize discussion periodic meetings. - Specify software requirement between Supervisor and project team before start of development.

- Give special

conflict in a meeting. - Report to Supervisor

- Discuss with

Supervisor to decide which requirement should be

implemented.

- Change requirement.

41/579

HVT Digital Transformation – Final Report v.1.1.9

**R4** Team members may distraction

**R5** Schedule may flaw

deadline and raise cost.

Team members may not pay

enough time for the project. Therefore, project may be over deadline.

- Time for one task can be too long or too short.

- Trouble may

occurs during

process that makes task longer than expected

Supervisor may

Human

Estimates

Team members are busy with studying while doing project

- The project is planned

assuming that all will take the most optimistic path possible.

- Poor plan

analysis.

- Poor team

member

assessment.

Communicate

Low High High High

consideration in

requirements.

- Understand team

members' schedule and assign suitable tasks and set appropriate deadlines.

- Require team members to set high priority for the project.

Use the Trello tool to add deadlines for important tasks and remind team members to always follow deadlines.

Develop for new

required functions. - Arrange team work frequently.

- Sketch deadline for the assigned tasks.

- Assign tasks to other members.

- A member who has free time involve in and support to finish the task.

- If there is some task that has more time than usual, member who take responsibilities should help each other.

- Create new time schedule.

**R6**

Lack of

Supervisor support

have not enough time to support project team. Therefore, the

Human

with the

Supervisor

inefficiently.

The supervisor is

Low High Define a meeting schedule with the Supervisor.

Ask for support from other sources.

42/579

HVT Digital Transformation – Final Report v.1.1.9

**R7** Lack the number of unit testing

The project team

work may get more mistakes.

Team members are can unable to

complete the

implementation of unit testing.

Therefore, when customers use the system, the system may have many bugs.

Members can’t find project documents.

Estimate, Human

a busy personal business and

support many teams at the same time

Lack of

implementation time.

Lack of close supervision

Lack of

Medium High

- Assigning the number of unit tests exactly for each member.

- Scrum master checks the testing progress.

- Save documents in multiple sources such as PC, Driver,...

Create and implement more unit test.

**R8**

may lost project documents

Therefore, it

spends lots of time writing again.

Two or members in team can do same

Human

managing

documents.

- Assign the work for team

members

Medium Medium

- The scrum master manages documents closely.

Create new documents. Use backup version,

**R9** Source code may be conflicted

one part.

Therefore, system may not run.

Human

inefficient.

- Member don't understand their task.

High High Pull source code before commit the source code.

discuss with other members and continue to work.

43/579

HVT Digital Transformation – Final Report v.1.1.9

**R10 R11**

**R12**

The system may not run in

updated web browser

The project team may

communicate with customer hardly

The project team may lost

member

Some element don't perform well in the web browser.

Therefore, system may not run.

There is some

misunderstanding between the

developer team and customers.

Therefore, the

project team may not solve the

problem of

customers.

The team may not be enough member to develop.

Therefore, project may be over

deadline.

All team members quarantine

Technology Human

Human

Web don't

support for

system

Long-distance between the

developer team and customer.

- When team

members got sick or had accident.

- Be isolated

from corona virus infection.

Low Medium Medium High

Low High

Give a list browser for customers that can run application fluently.

- Communicate frequently in online media.

- Reporting on a specific date with the customer.

- Leader remind members to take care their health

- Members protect

themselves carefully.

Consider and update the website to satisfy the new browser

version.

Come and discuss directly with

customers.

- Assign the task of missing members to others.

- Ask support from the external resource.

**R13** The team may work online

themselves at

home. Therefore, team members may not lose connection with others and

Disease Outbreak of

coronavirus. Low High None

Make new planning to development project online.

44/579

HVT Digital Transformation – Final Report v.1.1.9

**R14** Product owner may be changed

take more time to finish tasks.

The customer will be disabled to authorize the

managing system. Therefore, it

spends more time to transfer the system.

Human

Customers are busy or to

transfer new work.

Low Medium None

Tranfer the project for new customers who will manage this

system in the future.

**7.5.2. Risk description of Sprint 1**

**No. Risk Name Description Category Route cause Probability ImpactRisk response Risk Contingency Risk Mitigation**

Team members

may have trouble

that they should do

**R15**

Team members may

misunderstand the scrum

process.

exactly in the

project like what is the daily meeting should discuss, what is the scrum master. Therefore, the work may be not finished.

Any report doesn't

Human

Team members don't research about the scrum process.

Team members

Medium High

Leader send the scrum process tutorial for team members.

Leader assigns the

Scrum master retrain team members about the scrum process.

Team members use

**R16** The report may be over deadline

summit for the supervisor on-time. Therefor, it may

Human

don't focus on their task.

High High

specific work for each member.

more effort to finish their task.

45/579

HVT Digital Transformation – Final Report v.1.1.9

**R17 R18**

The designed database may be failure

Demo code on server task may be not done

affect to other

works.

The created

database is not working well in the project system and it has not a good architecture.

Therefore, team members may

spend more time to design the database again and

implement code late.

The demo code is not shown on-time. Therefore,

customer may be not satisfied.

Human Human

Team members have not to

experience

designing a good database.

- Team members don't focus on their task.

- The task is not estimated exactly.

High High High High

- Team members

researchers more about how to design a database.

- Team members discuss and review the project database.

Scrum master check the task deadline of each members.

Ask the support from the supervisor or the database expert.

- Team members use more effort to finish their task.

- Scrum master set a new deadline for their task.

**7.5.3. Risk description of Sprint 2**

**No. Risk Name Description Category Route cause Probability ImpactRisk response Risk Contingency Risk Mitigation**

**R19** Logic Bug

Team members may misunderstand flowchart of

Human

- Team members don't focus on their task.

High High

- Scrum master check the task deadline of each members.

- Team members use more effort to finish their task.

46/579

HVT Digital Transformation – Final Report v.1.1.9

function.

Therefore, team members may

spend more time to fix bug.

Team members

- Document is not

enough detailed.- Scrum master check source code.

- Team members

- Scrum master set a new deadline for their task.

- Team member

updates document.

**R20** Source code may conflict

push wrong branch in github.

Therefore, team members may

spend more time to restore code.

Team members may not have

enough knowledge about new

Human

don't focus on their task.

- Team members misunderstand commit code process.

The first time

High High

- Scrum master guides using github process.

- Scrum master check request merger of team members.

Team members ask scrum master to solve problems.

Team members ask

**R21** Risk about technique

The project team

technology to

develop. Therefore, team members may spend time to

research new

technology.

Team members may contact with

Human

team members use spring frame work

- Long-distance between the

High High Team members spend more time to research.

Team members are more

proactive to contact and

master about spring boot to support.

Team members proceed develop function follow

**R22**

may contact with customer hardly

customer hardly that about

exchange more

Human

developer team and customer.

High High

get an appointment with the customer for

convenient working time.

explicit request in advance.

47/579

HVT Digital Transformation – Final Report v.1.1.9

**R23**

The project team may create

sketchy design for modules

about project

requirements.

Therefore, the

working process may be lated.

The team members may create sketchy designs for

modules.

Therefore, the

system may happen a lot of bug and spend more time designing again.

Human

- Customers are teacher so they are busy on end of year.

Team members have not enough time and contact hardly with

customer.

High High

Team members arrange the working schedules to fit with customer's

working time.

Team members use more effort to design again.

**7.5.4. Risk description of Sprint 3**

**No. Risk Name Description Category Route cause Probability ImpactRisk response Risk Contingency Risk Mitigation**

- Team members use

**R24** Logic Bug

Team members may misunderstand flowchart of

function.

Therefore, team members may

spend more time to fix bug.

Human

- Team members don't focus on their task.

- Document is not enough detailed.

Medium High

- Scrum master check the task deadline of each members.

- Scrum master check source code.

more effort to finish their task.

- Scrum master set a new deadline for their task.

- Team member

updates document.

48/579

HVT Digital Transformation – Final Report v.1.1.9

**R25**

May execute wrong testing process

Team members may make mistake about how to

execute test

process. Therefore, it may spend more time to test again.

Team members push wrong branch in github.

Human

Team members don't have

experience of testing.

- Team members don't focus on their task.

High High

Team members

researchers more about how to testing.

- Scrum master guides using github process.

Ask support from the external resource.

Team members ask

**R26** Source code may conflict

The working

Therefore, team member may spend more time restoring code.

Team members may not have

Human

- Team members misunderstand commit code process.

Team members have to spend

High High

- Scrum master check request merger of team members.

Scrum master assign tasks

scrum master to solve problems.

Team members use

**R27 R28**

time may be limited

The solution for assigned redstar may have the problem

enough time to finish their tasks

May not find the best solution to solve the assigned Redstar

automatically. Therefore, the system may not do mission well.

Human Human

time for

assignments in class

The assigned problem is very complicated and spent more effort to solve

High High Medium High

effectively with the team members time.

Team members

researchers more about similar problems and how to solve them.

more effort to finish their task.

Ask support from the supervisor.

49/579

HVT Digital Transformation – Final Report v.1.1.9

**7.5.5. Risk description of Sprint 4**

**No. Risk Name Description Category Route cause Probability ImpactRisk response Risk Contingency Risk Mitigation**

- Team members use

**R29** Logic Bug May execute

Team members may misunderstand flowchart of

function.

Therefore, team members may

spend more time to fix bug.

Team members may make mistake about how to

Human

- Team members don't focus on their task.

- Document is not enough detailed.

Team members don't have

Low High

- Scrum master check the task deadline of each members.

- Scrum master check source code.

Team members

more effort to finish their task.

- Scrum master set a new deadline for their task.

- Team member

updates document. Ask support from the

**R30**

wrong testing process

execute test

process. Therefore, it may spend more time to test again.

Team members push wrong branch in github.

Human

experience of testing.

- Team members don't focus on their task.

Low Medium

researchers more about how to testing.

- Scrum master guides using github process.

external resource. Team members ask

**R31** Source code may conflict

Therefore, team member may spend more time restoring code.

Human

- Team members misunderstand commit code process.

Medium High

- Scrum master check request merger of team members.

scrum master to solve problems.

50/579

HVT Digital Transformation – Final Report v.1.1.9

**R32**

Overtime dateline of deploying

Team members may have the

problem with how to deploy project. Therefore, it may affect other works and make

customers

dissatisfied.

Team members lost a week for

Human

Team members don't have

experience of deploying.

Team member

High High

Team members

researchers more about how to deploying.

Ask support from the external resource.

Team members use

**R33** The deadline may not on-time

examination.

Therefore,

member's task may not finish on time. Communication with customer

Human

has to finish their final examination for a week.

High High None

more effort to finish their task.

**R34**

The project team may contact with customer hardly

hardly. Therefore, the project team may not solve the problem of

customers.

Human Covid-19 is

spread again. High High None

Team members work on online media like google meet.

**7.5.6. Probability – Impact matrix**

**y**High R1, R5, R9, R16, R17, R18, R19, R21, R22, R23,

R25, R26, R27, R32, R33, R34

**t**

**i**

Medium R8 R2, R3, R7, R11, R15. R24, R28, R31

**l**

**i**

**b**

**a**

Low R10, R14, R30 R4, R6, R12, R13, R29 **b**

**o**

Low Medium High

**r**

**P**

**Impact**

51/579

HVT Digital Transformation – Final Report v.1.1.9

**7.6. Risk Implement**

**No. Risk Contingency Risk Mitigation Other Risk Mitigation**

**Occurrent Status**

- Do well at the training together.

- Find materials and self-study.

**R1**

- The scrum master should understand the ability of each team member and assign the right work for the right person.

- Assign more team members to support or to do the task.

- Ask for the support of external others.

None Yes

**R2** - Clear requirement.

- Organize discussion periodic meetings.

- Specify software requirement between Supervisor and project

- Negotiate to deal with conflict in a meeting.

- Report to Supervisor

- Discuss with Supervisor to decide which

None Yes

team before start of development.

**R3**

- Give special consideration in requirements.

- Understand team members' schedule and assign suitable tasks

requirement should be implemented. - Change requirement. Develop for new required functions.

None Yes

and set appropriate deadlines.

**R4**

- Require team members to set high priority for the project.

None None No

- A member who has free time involve in

and support to finish the task.

**R5** Use the Trello tool to add deadlines for important tasks and remind team members to always follow deadlines.

- If there is some task that has more time than usual, member who take

responsibilities should help each other. - Create new time schedule

None No

**R6** Define a meeting schedule with the Supervisor. None None No **R7** - Assigning the number of unit tests exactly for each member.

- Scrum master checks the testing progress. None None No **R8** - Save documents in multiple sources such as PC, Driver... None None No **R9** Pull source code before commit the source code None None No

52/579

HVT Digital Transformation – Final Report v.1.1.9

**R10** None None None No **R11** - Communicate frequently in online media

- Reporting on a specific date with the customer None None No **R12** - Leader remind members to take care their health

- Members protect themselves carefully. None None No **R13** None None None No **R14** None None None No **R15** Leader send the scrum process tutorial for team members. None None No **R16** Leader assigns the specific work for each member. None None No

**R17**

- Team members researchers more about how to design a database.

- Team members discuss and review the project database.

Ask the support from the supervisor or the database expert.

- Team members use more effort to finish

Team member gives improved way

database

Yes

**R18** Scrum master check the task deadline of each members

- Scrum master check the task deadline of each members. **R19**

- Scrum master check source code.

**R20** - Scrum master guides using github process.

their task.

- Scrum master set a new deadline for their task.

- Team members use more effort to finish their task.

- Scrum master set a new deadline for their task.

- Team member updates document. Team members ask scrum master to solve

None Yes

None Yes Team members

- Scrum master check request merger of team members.

problems.

cancel request merge.

Yes

**R21** Team members spend more time to research. None None No

**R22** Team members are more proactive to contact and get an appointment with the customer for convenient working time

Team members proceed develop function

follow explicit request in advance. None Yes

53/579

HVT Digital Transformation – Final Report v.1.1.9

**R23** Team members arrange the working schedules to fit with

customer's working time. None None No - Team members use more effort to finish

**R24** - Scrum master check the task deadline of each members. - Scrum master check source code.

their task.

- Scrum master set a new deadline for their task.

- Team member updates document.

None Yes

**R25** Team members researchers more about how to testing. Ask support from the external resource. None Yes

**R26** - Scrum master guides using github process.

- Scrum master check request merger of team members. **R27** Scrum master assign tasks effectively with the team members time.

**R28** Team members researchers more about similar problems and how

Team members ask scrum master to solve

problems. None Yes Team members use more effort to finish

their task. None Yes

to solve them. Ask support from the supervisor. None Yes - Team members use more effort to finish

**R29** - Scrum master check the task deadline of each members. - Scrum master check source code.

their task.

- Scrum master set a new deadline for their task.

- Team member updates document.

None Yes

**R30** Team members researchers more about how to testing. None None No **R31** - Scrum master guides using github process.

- Scrum master check request merger of team members. None None No **R32** Team members researchers more about how to deploying. Ask support from the external resource. None Yes **R33** None Team members use more effort to finish

their task. None Yes

**R34** None Team members work on online media like google meet. None Yes

54/579

HVT Digital Transformation – Final Report v.1.1.9

**8. QUALITY MANAGEMENT**

**8.1. Quality Management Overview**

**8.1.1. Organization, Role and Responsibilities for quality management**

**Name Role Responsibilities** - Helps define product quality

Tran Binh Duong Supervisor

Vu Bao Yen Scum Master

Team members:

expectations.

- Determines final acceptance product’s quality

- Create quality plan

- Facilitate resolution of quality issues, escalating as needed.

- Create test plan

- Nguyen Tung Lam - Pham Trong Kim - Nguyen Thi Kim Loan

Developer

- Create test cases - Execute text cases - Report test result

HVT Gifted High School Tester - Execute acceptance tests.

**8.1.2. Tools, Environment, and Interfaces**

**Tool Description**

Cause-and-effect diagram

Used to find the root cause problem when there is a complaint about quality problems.

Flowchart Used to illustrate a solution model for a problem.

**8.2. Quality Planning**

**8.2.1. Define Project Quality**

❖ **System output:**

- A Web application supports evaluating the emulation grades, managing school activities and timetables.

❖ **Functionality:**

- Follow the requirements of the project.

❖ **Performance:**

- Time delay for system processing is less than 10s.

❖ **Reliability:**

- The application is available 24/7.

- Server can handle a least 200 clients concurrently.

55/579

HVT Digital Transformation – Final Report v.1.1.9

❖ **Maintainability:**

- Web applications are easy to be updated without any crashes. Source code is readability, complies with coding convention.

- System has to be designed to be easy to extend.

❖ **Security:**

- Information of admin and manager on server is secured.

**8.2.2. Measure Project Quality**

**Metric Goal**

Response of the web application Time delay for image processing <= 10s UT: 8 – 9 bugs / KLOC

Bugs/Lines of Code

ST: 2 – 4 bugs / KLOC ( based on Fsoft norms)

Maximum deep of loops <= 4

Algorithm complexity <= O(n^2)

Website support browser Support Chrome version 41.0.xxx.

**8.2.3. Improve Project Quality**

**Issue Action**

Difficult to track project’s progress

- Weekly report, team work 6 days/ week - Using Trello to track team members’ work

Maintainability - Specify coding conventions document - Concentrate on architecture design

Low quality code - Peer review, peer coding among developers

- Teambuilding to increase communication ability

between project’s members

Reward and discipline

- Have punishment rules when:

+ Submit terrible code (which causes to re coding more than 10%)

+ Miss deadline

Acceptance of users Conduct meetings face-to-face and contacts through Facebook, email, phone.

56/579

HVT Digital Transformation – Final Report v.1.1.9

**8.3. Quality Control**

**Deliverables Goal Quality control activity**

Designer has to:

**Frequency / Interval**

Interface Design Software

- Good looking & easy-to-use.

- Cover all

functions

specified in SRS Design to be easy to

- Ask for advice of some other designer

- Take comment from friends on completed work - Have approve from SRS leader

Have review and judgment

Each time design a new screen

Architecture Design

Integration Test Report

System Test

Report

extend

4 – 5 test cases/ function

Equal or greater than Integration test

from Supervisor On completion design

Scum Master requires

testers to report on work. Twice in a month. Scum Master requires

testers to report on work Twice in a month.

57/579

HVT Digital Transformation – Final Report v.1.1.9

**CHAPTER 3: SOFTWARE REQUIREMENTS SPECIFICATION**

**1. INTRODUCTION**

**1.1. Purpose**

This document provides developers, testers, QAs a complete and comprehensive description of both the functional requirement and non-functional requirements of the HTV Digital Transformation System. Developers base on this document to develop the system, and testers base on this to assure the quality of the output system. Scrum master

based this document to create a schedule and assign tasks to team members.

**1.2. Scope**

This document defines all functional and nonfunctional requirements for HTV Digital Transformation System.

**1.3. Overview**

Section 2 of this document provides overall information of the project, while excluding the specific requirements. Instead, it provides the background for those requirements, which are defined in Section 3.

Section 3 describes all the requirements in detail, including functional requirements and non-functional requirements. Each function is described based on the following format:

- Use Case: the detailed description of all use cases.

- Screen: The mockup/prototype of the screen which describes the workflow of the Use Case.

**2. OVERALL DESCRIPTION**

**2.1. Scope of work**

Project team will develop a Web Application for users to manage the emulation grade, activities and timetable of HVT Gifted High School.

The Application includes below main module:

- Manage account

- Manage class

- Manage timetable

- Manage violation of class

- Manage newsletter of school

58/579

HVT Digital Transformation – Final Report v.1.1.9

**3. BUSINESS PROCESS MANAGEMENT**

**3.1. Business Process of Manage Emulation**

Business process of manage emulation describe the management of the emulation

*Figure 20: Business process flow of "Manage Emulation"*

**3.2. Business rules**

**Business Rule Rule Description**

BR\_01 Only admins have the right to manage the account, teacher, and class. BR\_02 - The monitor, Red Star account require the information that is class. - All accounts require username and password.

BR\_03 Admins can delete all account except their account.

BR\_04 Teacher's identifier name must be unique.

BR\_05 When class is locked, monitor and Red Star accounts will be locked too. BR\_06 Class's identifier name must be unique.

BR\_07 Gifted class name must be unique.

BR\_08 Admins do not delete with gifted classes that have active classes. BR\_09 A class have one or more timetable.

BR\_10 Only admins and timetable managers can add timetables.

59/579

HVT Digital Transformation – Final Report v.1.1.9

BR\_11 When a new timetable adding, if the applying date is same with old timetable, the system will override timetable.

BR\_12 A violation type can have zero, one, and more violations. BR\_13 The violation must have belonged to only one violation type. BR\_14 The grade must be a positive number.

BR\_15 Can not delete a violation type that has any violations. BR\_16 Only admins can create and delete the assigned Red Star. BR\_17 When admins create a new assigned Red Star, the assigned red stars have apply date is bigger or equal imported date will be overridden.

BR\_18 Only admins have the right to add or delete the entering time. BR\_19 The entering time can be only added for Red Stars and summarizing groups.

BR\_20 The violation can be edited when the created date is not ranked in any weeks.

BR\_21 Admins have the right to add and edit the emulation grade of all classes at any time that is not ranked in any weeks.

BR\_22 The summarizing group has the right to grade emulation in the entering time of them.

BR\_23 Red Stars have the right to grade or edit a class that is assigned for them at the current day and with the entering time of them.

BR\_24 Monitors have the right to request change for any violations that are created in the current date.

BR\_25 Admins have the right to view all change requests.

BR\_26 Monitors have the right to view their change requests. BR\_27 Admins have the right to accept or reject any change requests that are not censored.

BR\_28 Monitors have the right to cancel their requests that are not censored. BR\_29 Only admins have the right to create or edit the week rank, the month rank, the semester rank, and the year rank.

BR\_30 Can not edit the week/month/semester rank that is ranked in the corresponding month/semester/year.

When week rank grade updating, all grades must be a positive number; the

BR\_31

learning grade must be smaller than 20, the movement grade and the labor grade must be smaller than 0.2.

BR\_32 Admins have the right to create newsletter directly.

BR\_33 Monitors and club leaders have the right to request create new newsletters. BR\_34 Monitors and club leaders have the right to view/edit/delete newsletters with not censor status yet.

BR\_35 Admins have the right to censor the created newsletter request that is not accepted yet.

BR\_36 Admins have right to edit/delete/post with all newsletters.

60/579

HVT Digital Transformation – Final Report v.1.1.9

**3.3. Modeling the problem "Assignment of Red Stars"**

**3.3.1. Problem**

In the process flow of "Manage Emulation" have Step is “Add assignment of Red Stars”, that is an important step in the process. This step requires the system to create an “Assignment of Red Star” table automatically so that each assignment of each Red Star in this table suitable for the “Assignment rules”.

“Assignment rules” is stated as follows:

∙ There are n Classes, each Class has more than or equal to two Red Stars. ∙ Find a way to be assigned Red Stars satisfies the following condition: 1. Each class will be estimated by two Red Star in two different Classes 2. Class's Red Stars of the same grade that are not assigned for each other (for example, the Red Stars of Classes belonging to tenth grade will not be assigned for other Classes belonging to tenth grade).

3. If the Red Stars of Classes assigned for other Classes in previous week. Then the next week Red Stars of other Classes will not continue assigning for Classes and do not reverse (for example, in week 1, Red Stars of Class B and Class C assigned for Class A and two Red Stars of Class A assigned for Class D and Class E. Then in week 2, Class A will not be estimated by Class B, C, D, E).

**3.3.2. Modeling the problem**

- Call N denotes the total number of Classes

- Call lj denotes Class j (j ∈ N)

- Call Kj denotes the grade of Class j

- Call Mj denotes the total number of Red Stars that Class j has

- Call sd (i, m) denotes the m-th Red Star of Class i (i ∈ N and m ∈ Mi) - Call X (i, m, j) denotes assigned or not-assigned relationship of the m-th Red Star of Class i with respect to Class j.

⮚ X (i, m, j) = 1 => m-th Red Star of Class *i* assigned for Class *j*

⮚ X (i, m, j) = 0 => m-th Red Star of Class *i* is not assigned for Class *j*

- Call S = {(i, m, j) | (i, j ∈ N) ˄ (m ∈ Mi)} denotes the relation set of the m-th Red Star of class i that assigned Class j in the previous week.

- Find a solution that X (i, m, j) ∀ i, m, j suitable with the following conditions: **Condition 1**: Each Class will be estimated by two Red Stars in two different Classes.

61/579

HVT Digital Transformation – Final Report v.1.1.9

N

Mi

∑∑X(i, m, j)=2

∀ j ∈N

i=1 Mi

m=1

{

∑X(i, m, j) ≤ 1 m=1

∀ i, j ∈N

**Condition 2:** Class's Red Stars of the same grade that are not assigned for each other.

���� (���� = ����) => ��(��, ��,��) = 0 ∀ i, j ∈ N , ∀ m ∈ Mi

**Condition 3**: If the Red Stars of Classes assigned for other Classes in previous week. Then the next week Red Stars of other Classes will not continue assigning for Classes and do not reverse.

���� (i,m, j) ∈ S => {X(i, m', j) = 0 ∀ m′ ∈ Mi

X(j, m', i) = 0 ∀ m′ ∈ Mi

**3.3.3. Modeling the problem to optimization**

- Call T (s, h, l) denotes a binary value show that X (s, h, l) violate or not violate the “Assignment rules”.

⮚ T (s, h, l) = 0 when X (s, h, l) DO NOT violate the “Assignment rules”. ⮚ T (s, h, l) = 1 when X (s, h, l) violate the “Assignment rules”.

- X (s, h, l) NOT violate the “Assignment rules” when suitable with the one of following conditions:

**Condition 1:** There are more than two Red Stars assigned for Class ��

s

h

∑∑X(i, m, l) ≥ 2

∀ s, l ∈ N , ∀h ∈ Ms

i=1

m=1

**Condition 2:** There are less than two Red Stars assigned for Class ��

s

h

∑∑X(i, m, l) ≤ 1

∀ l ∈ N, s = N − 1, h = Ms

i=1

OR

s

m=1 h

∑∑X(i, m, l) < 2

∀ l ∈ N, s = N, h = Ms

i=1

m=1

**Condition 3:** There are more than or equal to two Red Stars in the same Class assigned for Class ��

h

∑ X(s, m, l) ≥ 2 ∀ s, l ∈ N , ∀h ∈ Ms

��=1

**Condition 4:** Class's Red Stars of the same grade that are assigned for each other.

62/579

HVT Digital Transformation – Final Report v.1.1.9

(Ks = Kl) ˄ (X(s, h, l) = 1) ∀ s, l ∈ N ,∀h ∈ Ms

**Condition 5:** The Red Stars are Classes assigned for other Classes in previous week and in the next week Red Star of other classes will continue assigning for Classes or reverse.

X(s, h, l)=1 ˄ [( ∃(s, m, l) ∈ S , ∀ m ∈ Ms ) ˅ ( ∃(l,m, s) ∈ S ,∀ m ∈ Ms )]

- Find a solution that optimizes the smallest number of “X (s, h, l) violate the “Assignment rules” ”.

N

Ms

N

∑∑∑T(s, h, l) → Min

s=1

h=1

l=1

**4. FUNCTIONAL REQUIREMENTS**

**4.1. Module 1: Manage Account**

**4.1.1. Use Case Diagram**

*****Figure 21: Use Case Diagram of Manage Account Module*

**4.1.2. Use Case Description**

**4.1.2.1. Login use case**

****63/579

HVT Digital Transformation – Final Report v.1.1.9 

64/579

HVT Digital Transformation – Final Report v.1.1.9

**UC ID and Name: UC-1: Login**

Created By: Nguyen Tung Lam Date Created:

Primary Actor: All users Secondary Actors:

13/06/2020

HVT Digital Transformation System

Trigger: Users indicate that they want to login in system.

Description: This use case describes how user login in system. Precondition: Load Login Page.

Postconditions: System access with account of customer and switch to Home page.

Normal Follow: 1. User press “ĐĂNG NHẬP” in menu to send request login to system.

2. System give form to login.

3. User fills username and password in form.

4. User press button “Đăng nhập” to send information

account.

5. System send success dialog “Đăng nhập thành công!”.

6. User press button “Xác nhận”.

7. System directs to Home page with account.

Alternative Flows: None

Exceptions: Exception 4.1: Username doesn’t exist

1. System send the error message: “Tên đăng nhập không

tồn tại”.

Exception 4.2: Password isn’t correct

1. System send the error message: “Mật khẩu không

đúng”.

Exception 4.3: Username is empty

1. System send the error message: “Hãy điền tên đăng

nhập”.

Exception 4.4: Password is empty

1. System send the error message: “Hãy điền mật khẩu”.

Exception 4.5: Forget password

1. User click link “Quên mật khẩu?”.

2. System direct to new page include phone of the account

manager.

Exception 4.6: Username and password are empty

1. System send the error message: “Hãy điền tên đăng

nhập và mật khẩu.”.

Priority: High

Business Rules: None

65/579

HVT Digital Transformation – Final Report v.1.1.9 

*Figure 22: Activity diagram for login*

66/579

HVT Digital Transformation – Final Report v.1.1.9

**4.1.2.2. Logout use case**

****

**UC ID and Name: UC-2: Logout**

Created By: Nguyen Tung Lam Date Created:

Primary Actor: All users Secondary Actors:

Trigger: Users indicate that they want to logout. Description: This use case describes how user logout. Preconditions: Users already login to the system.

13/06/2020

HVT Digital Transformation System

Postconditions: System direct to Home page without account. Normal Follow: 1. User press “ĐĂNG XUẤT” in menu icon to send request logout to system.

2. System directs to Home page without account.

Alternative Flows: None

Exceptions: None

Priority: High

Business Rules: None

67/579

HVT Digital Transformation – Final Report v.1.1.9 *Figure 23: Activity diagram for logout*

**4.1.2.3. View the personal information use case**

****68/579

HVT Digital Transformation – Final Report v.1.1.9 

**UC ID and Name: UC-3: View the personal information** Created By: Nguyen Tung Lam Date Created:

Primary Actor: All users Secondary Actors:

13/06/2020

HVT Digital Transformation System

Trigger: User indicate that they want view their personal information Description: This use case describes how users can view their personal information.

Preconditions: User already login to system

Postconditions: User see their information in system

69/579

HVT Digital Transformation – Final Report v.1.1.9

Normal Follow: 1. User press menu “THÔNG TIN TÀI KHOẢN” in icon avatar to send request view personal information to system

2. System sends the all information follow role of user

a. If role user as “Lớp trưởng” or “Cờ đỏ”, system

sends information include: “Tên đăng nhập”, “Lớp”,

“Chức vụ”.

b. If role user as “CLB”, system sends information

include: “Tên đăng nhập”, “CLB”, “Chức vụ”.

c. If role user as “Người xếp TKB”, “Nhóm tổng hợp

điểm” or “Admin”, system sends information include:

“Tên đăng nhập”, “Họ và tên”, “Số điện thoại”, “Email”,

“Chức vụ”.

Alternative Flows: None

Exceptions: None

Priority: High

Business Rules: None

*Figure 24: Activity diagram for view the personal information*

70/579

HVT Digital Transformation – Final Report v.1.1.9

**4.1.2.4. Edit the personal information use case**

****

****

71/579

HVT Digital Transformation – Final Report v.1.1.9 

**UC ID and Name: UC-4: Edit your personal information** Created By: Nguyen Tung Lam Date Created 13/06/2020

Primary Actor: Timetable Manager, Admin, Summarize

Group

Secondary Actors:

HVT Digital Transformation System

Trigger: User indicate that they want edit their personal information. Description: This use case describes how users can view their personal information.

Preconditions: 1. User already login to system.

2. User already view their information.

Postconditions: User’s information is updated in system and they can view them.

Normal Follow: 1. User press button “CHỈNH SỬA” in view information page to send request edit information to system.

2. System allow edit information include: “Họ và tên”,

“Email”, “Số điện thoại” in this page.

3. User edit information.

4. User press button “XONG” to send information to

system.

5. System update information and send success dialog

“Thông tin sửa thành công!”.

6. User press button “ĐÓNG”.

7. System displays new information in this page.

Alternative Flows: None

Exceptions: Exception 4.1: Phone is invalid

1. System send the error message “SĐT không đúng định

dạng.”.

Exception 4.2: Email is invalid

1. System send the error message “Email không đúng định

dạng.”.

Priority: High

Business Rules: None

72/579

HVT Digital Transformation – Final Report v.1.1.9 

*Figure 25: Activity diagram for edit the personal information*

73/579

HVT Digital Transformation – Final Report v.1.1.9

**4.1.2.5. Change password use case**

****

****

74/579

HVT Digital Transformation – Final Report v.1.1.9 

**UC ID and Name: UC-5: Change password** Created By: Nguyen Tung Lam Date Created:

Primary Actor: All users Secondary Actors:

13/06/2020

HVT Digital Transformation System

Trigger: User indicate that they want to chance account password. Description: This use case describes how user can change their account password.

Preconditions: 1. Account exists.

2. User already login to system.

Postconditions: User’s password update in system and they can login the system by the new password.

Normal Follow: 1. User press “ĐỔI MẬT KHẨU” in menu icon to send request to system.

2. System sends a new page that include the change password form.

3. User input information include “Mật khẩu cũ”, “Mật khẩu mới”, “Xác nhận mật khẩu mới”.

4. User press button “XÁC NHẬN” to send information to system.

5. System update new password and send success dialog “Mật khẩu thay đổi thành công!”.

6. User press button “ĐÓNG”.

75/579

HVT Digital Transformation – Final Report v.1.1.9

7. System direct to Login Page without account.

Alternative Flows: None

Exceptions: Exception 4.1: Required Information is empty

1. System send the error message “Hãy điền đầy đủ tất cả

các trường.”.

Exception 4.2: Old password is incorrect

1. System send the error message “Mật khẩu không đúng”.

Exception 4.3: Password is invalid

1. System send the error message “Mật khẩu không đúng

định dạng”.

Exception 4.4: The new password is the same as the old

password

1. System send the error message “Mật khẩu chưa thay đổi”.

Exception 4.5: Password confirm wrong

1. System send the error message “Mật khẩu xác nhận không

đúng.”.

Exception 4.6: Password confirm is empty

1. System send the error message “Hãy xác nhận lại mật

khẩu.”.

Priority: High

Business Rules: None

76/579

HVT Digital Transformation – Final Report v.1.1.9 

*Figure 26: Activity diagram for change password*

77/579

HVT Digital Transformation – Final Report v.1.1.9

**4.1.2.6. Reset multiple account password use case**

****

****78/579

HVT Digital Transformation – Final Report v.1.1.9 

**UC ID and Name: UC-6: Reset multiple account password**

Created By: Nguyen Tung Lam Date Created:

Primary Actor: Admin Secondary Actors:

13/06/2020

HVT Digital Transformation System

Trigger: Admin indicates that he/she wants to reset the account password of all accounts.

Description: This use case describes how admin can reset the account password of all accounts.

Preconditions: 1. Admin already login to system.

2. Admin already view list account.

Postconditions: Passwords of accounts have reseted

Normal Follow: 1. Admin click checkbox to select one or multiple accounts. 2. Admin click button “Đặt lại MK” to send request to

system.

3. System display popup include: “Mật khẩu mới”, “Xác

nhận mật khẩu mới”.

4. Admin input information.

5. Admin press button “XÁC NHẬN” to send new password to system.

6. System accept new password and send success dialog

“Mật khẩu đã được đặt lại”.

7. Admin press button “ĐÓNG”.

Alternative Flows: None

Exceptions: Exception 2.1: No account to be selected

1. System send the error message “Hãy chọn tài khoản mà

bạn muốn đặt lại mật khẩu

Exception 5.1: New password and confirm password are empty

1. System send the error message “Hãy điền đầy đủ tất cả các

trường.”.

Exception 5.2: New password is invalid

79/579

HVT Digital Transformation – Final Report v.1.1.9

1. System send the error message “Mật khẩu không đúng

định dạng”.

Exception 5.3: Password confirm wrong

1. System send the error message “Mật khẩu xác nhận không

đúng.”.

Exception 5.4: Confirm password is empty

1. System send the error message “Hãy xác nhận lại mật

khẩu.”.

Exception 5.5: New password is empty

1. System send the error message “Hãy điền mật khẩu mới.”.

Priority: High

Business Rules: None

*Figure 27: Activity diagram for reset multiple account password*

80/579